## 1 General
Cobre
Stockpile Worksheet #1
General Information |  | 2014-12-05
Applicant | Cobre Mining Company
Hanover, New Mexico 88401
Disturbed Surface Area (acres) | 858.776
Type of Operation | Existing/Surface/Copper
Current value before escalation | 16438122.4034
and discounting
Stockpiles, Main Tailings Impoundment, Surface Impoundments, Haul Roads, Borrow Areas, Wells and Continental Pit
Based on Projected EOY 2019 Mine Plan

## 2 Demo
Cobre
Stockpile Worksheet #2
Demolition | 2014-12-05
Demo cost are addressed elsewhere.
This page intentionally left blank.

## 3 Material
Cobre
Stockpile Worksheet #3
Material Handling Plan Summary Sheet | [5 empty] | 2014-12-05
Total Haul/Push Distance
Item | Description | Location 1 | Location 2 |  | Grade | Equipment
|  |  |  | (ft) | (%)
1100 | Regrade Top | SWRDF | - | 540 | see dozer | D11T CD
1101 | Regrade Top | MTI | - | 200 | see dozer | D11T CD
1102 | Regrade Outslope | MTI Reclaim Pond | - | 200 | see dozer | D11T CD
1103 | Regrade Outslope | MTI | - | 250 | see dozer | D11T CD
1104 | Dozer Assist | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | - | see dozer | D11T CD
1105 | Dozer Assist | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | - | see dozer | D11T CD
1106 | Dozer Assist | NOBS | SWRDF Top | - | see dozer | D11T CD
1107 | Dozer Assist | NOBS | Hanover Mountain Deposit | - | see dozer | D11T CD
1108 | Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | - | see dozer | D11T CD
1109 | Dozer Assist | OB-4 Stockpile | Low Grade WRF | - | see dozer | D11T CD
1110 | Dozer Assist | NOBS | MTI Reclaim Pond | - | see dozer | D11T CD
1111 | Dozer Assist | NOBS | MTI Top | - | see dozer | D11T CD
1112 | Dozer Assist | NOBS | MTI Outslope | - | see dozer | D11T CD
1113 | Dozer Assist | Reclaim Pond Outlet Channel | MTI Top | - | see dozer | D11T CD
1114 | Dozer Assist | NOBS | Tailing Pipeline Corridor | - | see dozer | D11T CD
1115 | Dozer Assist | NOBS | Grape Gulch Pond #3 | - | see dozer | D11T CD
1116 | Dozer Assist | NOBS | Magnetite Seepage Pond | - | see dozer | D11T CD
1117 | Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | - | see dozer | D11T CD
1118 | Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | - | see dozer | D11T CD
1119 | Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | - | see dozer | D11T CD
1120 | Dozer Assist | OB-4 Stockpile | North Tailings Decant Pond | - | see dozer | D11T CD
1121 | Dozer Assist | OB-4 Stockpile | East WRF Containment | - | see dozer | D11T CD
1122 | Dozer Assist | NOBS | Blackman's Seep (Pond #2) | - | see dozer | D11T CD
1123 | Dozer Assist | OB-4 Stockpile | Decant Pond #4 | - | see dozer | D11T CD
1124 | Dozer Assist | NOBS | Upper Creek Containment Pond 1 | - | see dozer | D11T CD
1200 | Load cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top |  |  | 992K
1201 | Load cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes |  |  | 992K
1202 | Load cover soil | NOBS | SWRDF Top |  |  | 992K
1203 | Load cover soil | NOBS | Hanover Mountain Deposit |  |  | 992K
1204 | Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area |  |  | 992K
1205 | Load cover soil | OB-4 Stockpile | Low Grade WRF |  |  | 992K
1206 | Load cover soil | NOBS | MTI Reclaim Pond |  |  | 992K
1207 | Load cover soil | NOBS | MTI Top |  |  | 992K
1208 | Load cover soil | NOBS | MTI Outslope |  |  | 992K
1209 | Load cover soil | Reclaim Pond Outlet Channel | MTI Top |  |  | 992K
1210 | Load cover soil | NOBS | Tailing Pipeline Corridor |  |  | 992K
1211 | Load cover soil | NOBS | Grape Gulch Pond #3 |  |  | 992K
1212 | Load cover soil | NOBS | Magnetite Seepage Pond |  |  | 992K
1213 | Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 |  |  | 992K
1214 | Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 |  |  | 992K
1215 | Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 |  |  | 992K
1216 | Load cover soil | OB-4 Stockpile | North Tailings Decant Pond |  |  | 992K
1217 | Load cover soil | OB-4 Stockpile | East WRF Containment |  |  | 992K
1218 | Load cover soil | NOBS | Blackman's Seep (Pond #2) |  |  | 992K
1219 | Load cover soil | OB-4 Stockpile | Decant Pond #4 |  |  | 992K
1220 | Load cover soil | NOBS | Upper Creek Containment Pond 1 |  |  | 992K
1300 | Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | 3630 | see Trucks | 777F
1301 | Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | 3630 | see Trucks | 777F
1302 | Haul cover soil | NOBS | SWRDF Top | 12559 | see Trucks | 777F
1303 | Haul cover soil | NOBS | Hanover Mountain Deposit | 5707 | see Trucks | 777F
1304 | Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | 600 | see Trucks | 777F
1305 | Haul cover soil | OB-4 Stockpile | Low Grade WRF | 1000 | see Trucks | 777F
1306 | Haul cover soil | NOBS | MTI Reclaim Pond | 7193 | see Trucks | 777F
1307 | Haul cover soil | NOBS | MTI Top | 7193 | see Trucks | 777F
1308 | Haul cover soil | NOBS | MTI Outslope | 7193 | see Trucks | 777F
1309 | Haul cover soil | Reclaim Pond Outlet Channel | MTI Top | 1172 | see Trucks | 777F
1310 | Haul cover soil | NOBS | Tailing Pipeline Corridor | 7193 | see Trucks | 777F
1311 | Haul cover soil | NOBS | Grape Gulch Pond #3 | 3856 | see Trucks | 777F
1312 | Haul cover soil | NOBS | Magnetite Seepage Pond | 6480 | see Trucks | 777F
1313 | Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | 3630 | see Trucks | 777F
1314 | Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | 3630 | see Trucks | 777F
1315 | Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | 3630 | see Trucks | 777F
1316 | Haul cover soil | OB-4 Stockpile | North Tailings Decant Pond | 1000 | see Trucks | 777F
1317 | Haul cover soil | OB-4 Stockpile | East WRF Containment | 1000 | see Trucks | 777F
1318 | Haul cover soil | NOBS | Blackman's Seep (Pond #2) | 3856 | see Trucks | 777F
1319 | Haul cover soil | OB-4 Stockpile | Decant Pond #4 | 1000 | see Trucks | 777F
1320 | Haul cover soil | NOBS | Upper Creek Containment Pond 1 | 3856 | see Trucks | 777F
1400 | Rip liners | East WRF Containment | - | 1000 |  | D11T w/ ripper
1401 | Rip liners | Decant Pond #4 | - | 1000 |  | D11T w/ ripper
1402 | Rip liners | Blackman's Seep (Pond #2) | - | 1000 |  | D11T w/ ripper
1403 | Rip liners | Grape Gulch Pond #3 | - | 1000 |  | D11T w/ ripper
1404 | Rip liners | Magnetite Seepage Pond | - | 1000 |  | D11T w/ ripper
1405 | Rip surface | Reclaim Pond Outlet Channel | - | 1000 |  | D11T w/ ripper
1406 | Rip liners | Upper Creek Containment Pond 1 | - | 1000 |  | D11T w/ ripper
1500 | Grade surface | Haul Roads | - |  |  | 16M
1501 | Grade surface | Exploration Roads | - |  |  | 16M
1502 | Grade surface | Low Grade WRF | - |  |  | 16M
1503 | Grade surface | Grape Gulch Pond #3 | - |  |  | 16M
1504 | Grade surface | Magnetite Seepage Pond | - |  |  | 16M
1505 | Grade surface | SWRF Dam 1 | - |  |  | 16M
1506 | Grade surface | SWRF Dam 2 | - |  |  | 16M
1507 | Grade surface | SWRF Dam 3 | - |  |  | 16M
1508 | Grade surface | North Tailings Decant Pond | - |  |  | 16M
1509 | Grade surface | East WRF Containment | - |  |  | 16M
1510 | Grade surface | Blackman's Seep (Pond #2) | - |  |  | 16M
1511 | Grade surface | Decant Pond #4 | - |  |  | 16M
1512 | Grade surface | Upper Creek Containment Pond 1 | - |  |  | 16M
1513 | Grade cover soil | SWRDF Top | - |  |  | D11T CD
1514 | Grade cover soil | SWRDF Outslopes | - |  |  | D11T CD
1515 | Grade cover soil | SWRDF Top | - |  |  | D11T CD
1516 | Grade cover soil | Hanover Mountain Deposit | - |  |  | D11T CD
1517 | Grade cover soil | Pearson-Barnes Mine Area | - |  |  | D11T CD
1518 | Grade cover soil | Low Grade WRF | - |  |  | D11T CD
1519 | Grade cover soil | MTI Reclaim Pond | - |  |  | D11T CD
1520 | Grade cover soil | MTI Top | - |  |  | D11T CD
1521 | Grade cover soil | MTI Outslope | - |  |  | D11T CD
1522 | Grade cover soil | MTI Top | - |  |  | D11T CD
1523 | Grade cover soil | Tailing Pipeline Corridor | - |  |  | D11T CD
1524 | Grade cover soil | Grape Gulch Pond #3 | - |  |  | D11T CD
1525 | Grade cover soil | Magnetite Seepage Pond | - |  |  | D11T CD
1526 | Grade cover soil | SWRF Dam 1 | - |  |  | D11T CD
1527 | Grade cover soil | SWRF Dam 2 | - |  |  | D11T CD
1528 | Grade cover soil | SWRF Dam 3 | - |  |  | D11T CD
1529 | Grade cover soil | North Tailings Decant Pond | - |  |  | D11T CD
1530 | Grade cover soil | East WRF Containment | - |  |  | D11T CD
1531 | Grade cover soil | Blackman's Seep (Pond #2) | - |  |  | D11T CD
1532 | Grade cover soil | Decant Pond #4 | - |  |  | D11T CD
1533 | Grade cover soil | Upper Creek Containment Pond 1 | - |  |  | D11T CD
1600 | Off-Hwy Water Tanker Truck |  |  |  |  | 10,000 gal
1601 | Motor Grader |  |  |  |  | 16M
OB = Overburden
WRF= Waste Rock Facility

## 4 Earthwork
Cobre
Stockpile Worksheet #4
Earthwork Quantity Worksheet | [7 empty] | 2014-12-05
[5 empty] | Cover | Bank/stockpile | Swell | Loose/stockpile
|  | Location 1 | Location 2 | Area | Depth | Volume | Factor | Volume
Item | Description |  |  | (ac) | (in) | (bcy) | (%) | (lcy)
1100 | Regrade Top | SWRDF | Top |  |  | 666680 | 0% | 666680
1101 | Regrade Top | MTI | Top |  |  | 50794.5 | 0% | 50794.5
1102 | Regrade Outslope | MTI Reclaim Pond | Top and Outslope |  |  | 67765 | 0% | 67765
1103 | Regrade Outslope | MTI | Outslope |  |  | 170294 | 0% | 170294
1104 | Dozer Assist | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top |  |  | 412368 | 0% | 412368
1105 | Dozer Assist | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes |  |  | 1237104 | 0% | 1237104
1106 | Dozer Assist | NOBS | SWRDF Top |  |  | 119548 | 0% | 119548
1107 | Dozer Assist | NOBS | Hanover Mountain Deposit |  |  | 451572 | 0% | 451572
1108 | Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area |  |  | 57596 | 0% | 57596
1109 | Dozer Assist | OB-4 Stockpile | Low Grade WRF |  |  | 44899.0667 | 0% | 44899.0667
1110 | Dozer Assist | NOBS | MTI Reclaim Pond |  |  | 159720 | 0% | 159720
1111 | Dozer Assist | NOBS | MTI Top |  |  | 190284.1 | 0% | 190284.1
1112 | Dozer Assist | NOBS | MTI Outslope |  |  | 175837.2 | 0% | 175837.2
1113 | Dozer Assist | Reclaim Pond Outlet Channel | MTI Top |  |  | 62226 | 15% | 71559.9
1114 | Dozer Assist | NOBS | Tailing Pipeline Corridor |  |  | 6998.64 | 0% | 6998.64
1115 | Dozer Assist | NOBS | Grape Gulch Pond #3 |  |  | 1839.2 | 0% | 1839.2
1116 | Dozer Assist | NOBS | Magnetite Seepage Pond |  |  | 968 | 0% | 968
1117 | Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 |  |  | 2516.8 | 0% | 2516.8
1118 | Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 |  |  | 1645.6 | 0% | 1645.6
1119 | Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 |  |  | 4065.6 | 0% | 4065.6
1120 | Dozer Assist | OB-4 Stockpile | North Tailings Decant Pond |  |  | 2226.4 | 0% | 2226.4
1121 | Dozer Assist | OB-4 Stockpile | East WRF Containment |  |  | 2420 | 0% | 2420
1122 | Dozer Assist | NOBS | Blackman's Seep (Pond #2) |  |  | 48.4 | 0% | 48.4
1123 | Dozer Assist | OB-4 Stockpile | Decant Pond #4 |  |  | 3000.8 | 0% | 3000.8
1124 | Dozer Assist | NOBS | Upper Creek Containment Pond 1 |  |  | 5469.2 | 0% | 5469.2
1200 | Load cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | 85.2 | 36 | 412368 | 0% | 412368
1201 | Load cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | 255.6 | 36 | 1237104 | 0% | 1237104
1202 | Load cover soil | NOBS | SWRDF Top | 24.7 | 36 | 119548 | 0% | 119548
1203 | Load cover soil | NOBS | Hanover Mountain Deposit | 93.3 | 36 | 451572 | 0% | 451572
1204 | Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | 11.9 | 36 | 57596 | 0% | 57596
1205 | Load cover soil | OB-4 Stockpile | Low Grade WRF | 27.83 | 12 | 44899.0667 | 0% | 44899.0667
1206 | Load cover soil | NOBS | MTI Reclaim Pond | 33 | 36 | 159720 | 0% | 159720
1207 | Load cover soil | NOBS | MTI Top | 108.2 | 18 | 190284.1 | 0% | 190284.1 | <- subtract cover already hauled from Reclaim Pond Outlet cut
1208 | Load cover soil | NOBS | MTI Outslope | 36.33 | 36 | 175837.2 | 0% | 175837.2
1209 | Load cover soil | Reclaim Pond Outlet Channel | MTI Top | - | - | 62226 | 15% | 71559.9
1210 | Load cover soil | NOBS | Tailing Pipeline Corridor | 1.446 | 36 | 6998.64 | 0% | 6998.64
1211 | Load cover soil | NOBS | Grape Gulch Pond #3 | 0.38 | 36 | 1839.2 | 0% | 1839.2
1212 | Load cover soil | NOBS | Magnetite Seepage Pond | 0.2 | 36 | 968 | 0% | 968
1213 | Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | 0.52 | 36 | 2516.8 | 0% | 2516.8
1214 | Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | 0.34 | 36 | 1645.6 | 0% | 1645.6
1215 | Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | 0.84 | 36 | 4065.6 | 0% | 4065.6
1216 | Load cover soil | OB-4 Stockpile | North Tailings Decant Pond | 0.46 | 36 | 2226.4 | 0% | 2226.4
1217 | Load cover soil | OB-4 Stockpile | East WRF Containment | 0.5 | 36 | 2420 | 0% | 2420
1218 | Load cover soil | NOBS | Blackman's Seep (Pond #2) | 0.01 | 36 | 48.4 | 0% | 48.4
1219 | Load cover soil | OB-4 Stockpile | Decant Pond #4 | 0.62 | 36 | 3000.8 | 0% | 3000.8
1220 | Load cover soil | NOBS | Upper Creek Containment Pond 1 | 1.13 | 36 | 5469.2 | 0% | 5469.2
1300 | Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top |  |  | 412368 | 0% | 412368
1301 | Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes |  |  | 1237104 | 0% | 1237104
1302 | Haul cover soil | NOBS | SWRDF Top |  |  | 119548 | 0% | 119548
1303 | Haul cover soil | NOBS | Hanover Mountain Deposit |  |  | 451572 | 0% | 451572
1304 | Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area |  |  | 57596 | 0% | 57596
1305 | Haul cover soil | OB-4 Stockpile | Low Grade WRF |  |  | 44899.0667 | 0% | 44899.0667
1306 | Haul cover soil | NOBS | MTI Reclaim Pond |  |  | 159720 | 0% | 159720
1307 | Haul cover soil | NOBS | MTI Top |  |  | 190284.1 | 0% | 190284.1
1308 | Haul cover soil | NOBS | MTI Outslope |  |  | 175837.2 | 0% | 175837.2
1309 | Haul cover soil | Reclaim Pond Outlet Channel | MTI Top |  |  | 62226 | 15% | 71559.9
1310 | Haul cover soil | NOBS | Tailing Pipeline Corridor |  |  | 6998.64 | 0% | 6998.64
1311 | Haul cover soil | NOBS | Grape Gulch Pond #3 |  |  | 1839.2 | 0% | 1839.2
1312 | Haul cover soil | NOBS | Magnetite Seepage Pond |  |  | 968 | 0% | 968
1313 | Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 |  |  | 2516.8 | 0% | 2516.8
1314 | Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 |  |  | 1645.6 | 0% | 1645.6
1315 | Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 |  |  | 4065.6 | 0% | 4065.6
1316 | Haul cover soil | OB-4 Stockpile | North Tailings Decant Pond |  |  | 2226.4 | 0% | 2226.4
1317 | Haul cover soil | OB-4 Stockpile | East WRF Containment |  |  | 2420 | 0% | 2420
1318 | Haul cover soil | NOBS | Blackman's Seep (Pond #2) |  |  | 48.4 | 0% | 48.4
1319 | Haul cover soil | OB-4 Stockpile | Decant Pond #4 |  |  | 3000.8 | 0% | 3000.8
1320 | Haul cover soil | NOBS | Upper Creek Containment Pond 1 |  |  | 5469.2 | 0% | 5469.2
1400 | Rip liners | East WRF Containment | - | 0.5
1401 | Rip liners | Decant Pond #4 | - | 0.62
1402 | Rip liners | Blackman's Seep (Pond #2) | - | 0.01
1403 | Rip liners | Grape Gulch Pond #3 | - | 0.38
1404 | Rip liners | Magnetite Seepage Pond | - | 0.2
1405 | Rip surface | Reclaim Pond Outlet Channel | - | 1.7
1406 | Rip liners | Upper Creek Containment Pond 1 | - | 1.13
1500 | Grade surface | Haul Roads | - | 45
1501 | Grade surface | Exploration Roads | - | 37
1502 | Grade surface | Low Grade WRF | - | 27.83
1503 | Grade surface | Grape Gulch Pond #3 | - | 0.38
1504 | Grade surface | Magnetite Seepage Pond | - | 0.2
1505 | Grade surface | SWRF Dam 1 | - | 0.52
1506 | Grade surface | SWRF Dam 2 | - | 0.34
1507 | Grade surface | SWRF Dam 3 | - | 0.84
1508 | Grade surface | North Tailings Decant Pond | - | 0.46
1509 | Grade surface | East WRF Containment | - | 0.5
1510 | Grade surface | Blackman's Seep (Pond #2) | - | 0.01
1511 | Grade surface | Decant Pond #4 | - | 0.62
1512 | Grade surface | Upper Creek Containment Pond 1 | - | 1.13
1513 | Grade cover soil | SWRDF Top | - |  |  | 412368 | 0% | 412368
1514 | Grade cover soil | SWRDF Outslopes | - |  |  | 1237104 | 0% | 1237104
1515 | Grade cover soil | SWRDF Top | - |  |  | 119548 | 0% | 119548
1516 | Grade cover soil | Hanover Mountain Deposit | - |  |  | 451572 | 0% | 451572
1517 | Grade cover soil | Pearson-Barnes Mine Area | - |  |  | 57596 | 0% | 57596
1518 | Grade cover soil | Low Grade WRF | - |  |  | 44899.0667 | 0% | 44899.0667
1519 | Grade cover soil | MTI Reclaim Pond | - |  |  | 159720 | 0% | 159720
1520 | Grade cover soil | MTI Top | - |  |  | 190284.1 | 0% | 190284.1
1521 | Grade cover soil | MTI Outslope | - |  |  | 175837.2 | 0% | 175837.2
1522 | Grade cover soil | MTI Top | - |  |  | 62226 | 15% | 71559.9
1523 | Grade cover soil | Tailing Pipeline Corridor | - |  |  | 6998.64 | 0% | 6998.64
1524 | Grade cover soil | Grape Gulch Pond #3 | - |  |  | 1839.2 | 0% | 1839.2
1525 | Grade cover soil | Magnetite Seepage Pond | - |  |  | 968 | 0% | 968
1526 | Grade cover soil | SWRF Dam 1 | - |  |  | 2516.8 | 0% | 2516.8
1527 | Grade cover soil | SWRF Dam 2 | - |  |  | 1645.6 | 0% | 1645.6
1528 | Grade cover soil | SWRF Dam 3 | - |  |  | 4065.6 | 0% | 4065.6
1529 | Grade cover soil | North Tailings Decant Pond | - |  |  | 2226.4 | 0% | 2226.4
1530 | Grade cover soil | East WRF Containment | - |  |  | 2420 | 0% | 2420
1531 | Grade cover soil | Blackman's Seep (Pond #2) | - |  |  | 48.4 | 0% | 48.4
1532 | Grade cover soil | Decant Pond #4 | - |  |  | 3000.8 | 0% | 3000.8
1533 | Grade cover soil | Upper Creek Containment Pond 1 | - |  |  | 5469.2 | 0% | 5469.2
1600 | Off-Hwy Water Tanker Truck
1601 | Motor Grader

## 5 Dozer
Cobre
Stockpile Worksheet #5
Productivity and Hours Required for Dozer Use---Earthmoving | [17 empty] | 2014-12-05
PERFORMANCE FACTORS
[6 empty] | Total |  |  |  | Production | Maximum | [5 empty] | Direct
|  |  |  | Loose |  | Task |  |  | Soil | Method/ | Push | Normal |  | Work |  |  | Drive | Grade
Task Description | Location 1 | Location 2 | Equipment | Volume | Productivity | Time | Material | Grade | Weight | Blade | Distance | Production | Operator | Hour | Visibility | Elevation | Trans.
|  |  |  | (cy) | (cy/hr) | (hours) | Factor | Factor | (lb/cy) | Factor | (feet) | (cy/hr) | Factor | (min/hr) | Factor | Factor | Factor | (%)
Regrade Top | SWRDF | Top | D11T CD | 666680 | 448.5707 | 1486.2316 | 1.2 | 1.02 | 3300 | 1.2 | 540 | 701.0909 | 0.75 | 50 | 1 | 1 | 1 | -1
Regrade Top | MTI | Top | D11T CD | 50794.5 | 1196.8147 | 42.4414 | 1.2 | 1.0154 | 2900 | 1.2 | 200 | 1651.2674 | 0.75 | 50 | 1 | 1 | 1 | -0.77
Regrade Outslope | MTI Reclaim Pond | Top and Outslope | D11T CD | 67765 | 1719.4197 | 39.4116 | 1.2 | 1.66 | 3300 | 1.2 | 200 | 1651.2674 | 0.75 | 50 | 1 | 1 | 1 | -33
Regrade Outslope | MTI | Outslope | D11T CD | 170294 | 1614.0418 | 105.5078 | 1.2 | 1.66 | 2900 | 1.2 | 250 | 1362.1795 | 0.75 | 50 | 1 | 1 | 1 | -33
Dozer Assist | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | D11T CD | N/A | N/A | 382.9131 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | D11T CD | N/A | N/A | 1148.7394 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | NOBS | SWRDF Top | D11T CD | N/A | N/A | 111.0089 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | NOBS | Hanover Mountain Deposit | D11T CD | N/A | N/A | 419.3169 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | D11T CD | N/A | N/A | 53.482 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | OB-4 Stockpile | Low Grade WRF | D11T CD | N/A | N/A | 41.692 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | NOBS | MTI Reclaim Pond | D11T CD | N/A | N/A | 148.3114 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | NOBS | MTI Top | D11T CD | N/A | N/A | 176.6924 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | NOBS | MTI Outslope | D11T CD | N/A | N/A | 163.2774 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | Reclaim Pond Outlet Channel | MTI Top | D11T CD | N/A | N/A | 66.4485 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | NOBS | Tailing Pipeline Corridor | D11T CD | N/A | N/A | 6.4987 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | NOBS | Grape Gulch Pond #3 | D11T CD | N/A | N/A | 1.7078 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | NOBS | Magnetite Seepage Pond | D11T CD | N/A | N/A | 0.89886 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | D11T CD | N/A | N/A | 2.337 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | D11T CD | N/A | N/A | 1.5281 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | D11T CD | N/A | N/A | 3.7752 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | OB-4 Stockpile | North Tailings Decant Pond | D11T CD | N/A | N/A | 2.0674 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | OB-4 Stockpile | East WRF Containment | D11T CD | N/A | N/A | 2.2471 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | NOBS | Blackman's Seep (Pond #2) | D11T CD | N/A | N/A | 0.044943 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | OB-4 Stockpile | Decant Pond #4 | D11T CD | N/A | N/A | 2.7865 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Dozer Assist | NOBS | Upper Creek Containment Pond 1 | D11T CD | N/A | N/A | 5.0785 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## 6 Grading
Cobre
Stockpile Worksheet #6
Productivity and Hours Required for Dozer Use---Grading | [21 empty] | 2014-12-05
PERFORMANCE FACTORS
[12 empty] | Production | Effective |  |  |  |  | Direct |  |  | Maximum
[8 empty] | Task |  |  | Soil | Method/ | Blade |  | Work |  |  | Drive |  |  | Push | Normal
Task Description | Location 1 | Location 2 | Equipment | Volume | Area | Productivity | Productivity | Time | Material | Grade | Weight | Blade | Width | Speed | Hour | Visibility | Elevation | Trans. | Grade | Operator | Distance | Production
|  |  |  | (cy) | (acres) | (acres/hr) | (cy/hr) | (hours) |  | Factor | (lb/cy) |  | (feet) | (miles/hr) | (min/hr) |  |  |  | (%) |  | (feet) | (cy/hr)
Grade surface | Haul Roads | - | 16M | - | 45 | 3.1021 |  | 14.5061 | 1.2 | 1.02 | 3300 | 1.2 | 16 | 2.5 | 50 | 1 | 1 | 1 | -1 | 0.75 | -
Grade surface | Exploration Roads | - | 16M | - | 37 | 3.1021 |  | 11.9272 | 1.2 | 1.02 | 3300 | 1.2 | 16 | 2.5 | 50 | 1 | 1 | 1 | -1 | 0.75 | -
Grade surface | Low Grade WRF | - | 16M | - | 27.83 | 3.1021 |  | 8.9712 | 1.2 | 1.02 | 3300 | 1.2 | 16 | 2.5 | 50 | 1 | 1 | 1 | -1 | 0.75 | -
Grade surface | Grape Gulch Pond #3 | - | 16M | - | 0.38 | 3.1021 |  | 0.1225 | 1.2 | 1.02 | 3300 | 1.2 | 16 | 2.5 | 50 | 1 | 1 | 1 | -1 | 0.75 | -
Grade surface | Magnetite Seepage Pond | - | 16M | - | 0.2 | 3.1021 |  | 0.064471 | 1.2 | 1.02 | 3300 | 1.2 | 16 | 2.5 | 50 | 1 | 1 | 1 | -1 | 0.75 | -
Grade surface | SWRF Dam 1 | - | 16M | - | 0.52 | 3.1021 |  | 0.16763 | 1.2 | 1.02 | 3300 | 1.2 | 16 | 2.5 | 50 | 1 | 1 | 1 | -1 | 0.75 | -
Grade surface | SWRF Dam 2 | - | 16M | - | 0.34 | 3.1021 |  | 0.1096 | 1.2 | 1.02 | 3300 | 1.2 | 16 | 2.5 | 50 | 1 | 1 | 1 | -1 | 0.75 | -
Grade surface | SWRF Dam 3 | - | 16M | - | 0.84 | 3.1021 |  | 0.27078 | 1.2 | 1.02 | 3300 | 1.2 | 16 | 2.5 | 50 | 1 | 1 | 1 | -1 | 0.75 | -
Grade surface | North Tailings Decant Pond | - | 16M | - | 0.46 | 3.1021 |  | 0.14828 | 1.2 | 1.02 | 3300 | 1.2 | 16 | 2.5 | 50 | 1 | 1 | 1 | -1 | 0.75 | -
Grade surface | East WRF Containment | - | 16M | - | 0.5 | 3.1021 |  | 0.16118 | 1.2 | 1.02 | 3300 | 1.2 | 16 | 2.5 | 50 | 1 | 1 | 1 | -1 | 0.75 | -
Grade surface | Blackman's Seep (Pond #2) | - | 16M | - | 0.01 | 3.1021 |  | 0.0032236 | 1.2 | 1.02 | 3300 | 1.2 | 16 | 2.5 | 50 | 1 | 1 | 1 | -1 | 0.75 | -
Grade surface | Decant Pond #4 | - | 16M | - | 0.62 | 3.1021 |  | 0.19986 | 1.2 | 1.02 | 3300 | 1.2 | 16 | 2.5 | 50 | 1 | 1 | 1 | -1 | 0.75 | -
Grade surface | Upper Creek Containment Pond 1 | - | 16M | - | 1.13 | 3.1021 |  | 0.36426 | 1.2 | 1.02 | 3300 | 1.2 | 16 | 2.5 | 50 | 1 | 1 | 1 | -1 | 0.75 | -
Grade cover soil | SWRDF Top | - | D11T CD | 412368 |  | - | 1920.9083 | 214.6734 | 1.2 | 1.02 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -1 | 0.75 | 100 | 3002.2721
Grade cover soil | SWRDF Outslopes | - | D11T CD | 1237104 |  | - | 3032.0219 | 408.0129 | 1.2 | 1.61 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -30.5 | 0.75 | 100 | 3002.2721
Grade cover soil | SWRDF Top | - | D11T CD | 119548 |  | - | 1920.9083 | 62.2351 | 1.2 | 1.02 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -1 | 0.75 | 100 | 3002.2721
Grade cover soil | Hanover Mountain Deposit | - | D11T CD | 451572 |  | - | 1920.9083 | 235.0825 | 1.2 | 1.02 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -1 | 0.75 | 100 | 3002.2721
Grade cover soil | Pearson-Barnes Mine Area | - | D11T CD | 57596 |  | - | 1242.9406 | 46.3385 | 1.2 | 0.66 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | 17 | 0.75 | 100 | 3002.2721
Grade cover soil | Low Grade WRF | - | D11T CD | 44899.0667 |  | - | 3126.184 | 14.3623 | 1.2 | 1.66 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -33 | 0.75 | 100 | 3002.2721
Grade cover soil | MTI Reclaim Pond | - | D11T CD | 159720 |  | - | 3126.184 | 51.091 | 1.2 | 1.66 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -33 | 0.75 | 100 | 3002.2721
Grade cover soil | MTI Top | - | D11T CD | 190284.1 |  | - | 1912.2453 | 99.5082 | 1.2 | 1.0154 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -0.77 | 0.75 | 100 | 3002.2721
Grade cover soil | MTI Outslope | - | D11T CD | 175837.2 |  | - | 3126.184 | 56.2466 | 1.2 | 1.66 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -33 | 0.75 | 100 | 3002.2721
Grade cover soil | MTI Top | - | D11T CD | 71559.9 |  | - | 1912.2453 | 37.4219 | 1.2 | 1.0154 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -0.77 | 0.75 | 100 | 3002.2721
Grade cover soil | Tailing Pipeline Corridor | - | D11T CD | 6998.64 |  | - | 1920.9083 | 3.6434 | 1.2 | 1.02 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -1 | 0.75 | 100 | 3002.2721
Grade cover soil | Grape Gulch Pond #3 | - | D11T CD | 1839.2 |  | - | 1920.9083 | 0.95746 | 1.2 | 1.02 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -1 | 0.75 | 100 | 3002.2721
Grade cover soil | Magnetite Seepage Pond | - | D11T CD | 968 |  | - | 1920.9083 | 0.50393 | 1.2 | 1.02 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -1 | 0.75 | 100 | 3002.2721
Grade cover soil | SWRF Dam 1 | - | D11T CD | 2516.8 |  | - | 1920.9083 | 1.3102 | 1.2 | 1.02 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -1 | 0.75 | 100 | 3002.2721
Grade cover soil | SWRF Dam 2 | - | D11T CD | 1645.6 |  | - | 1920.9083 | 0.85668 | 1.2 | 1.02 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -1 | 0.75 | 100 | 3002.2721
Grade cover soil | SWRF Dam 3 | - | D11T CD | 4065.6 |  | - | 1920.9083 | 2.1165 | 1.2 | 1.02 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -1 | 0.75 | 100 | 3002.2721
Grade cover soil | North Tailings Decant Pond | - | D11T CD | 2226.4 |  | - | 1920.9083 | 1.159 | 1.2 | 1.02 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -1 | 0.75 | 100 | 3002.2721
Grade cover soil | East WRF Containment | - | D11T CD | 2420 |  | - | 1920.9083 | 1.2598 | 1.2 | 1.02 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -1 | 0.75 | 100 | 3002.2721
Grade cover soil | Blackman's Seep (Pond #2) | - | D11T CD | 48.4 |  | - | 1920.9083 | 0.025196 | 1.2 | 1.02 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -1 | 0.75 | 100 | 3002.2721
Grade cover soil | Decant Pond #4 | - | D11T CD | 3000.8 |  | - | 1920.9083 | 1.5622 | 1.2 | 1.02 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -1 | 0.75 | 100 | 3002.2721
Grade cover soil | Upper Creek Containment Pond 1 | - | D11T CD | 5469.2 |  | - | 1920.9083 | 2.8472 | 1.2 | 1.02 | 3300 | 1.2 | - | - | 50 | 1 | 1 | 1 | -1 | 0.75 | 100 | 3002.2721
#VALUE! | #VALUE! | #VALUE! | #VALUE! | - | #VALUE! | 1.5838 |  | #VALUE! | 1.2 | 1 | 3300 | 1.2 | 20.83 | 1 | 50 | 1 | 1 | 1 | 0 | 0.75 | - | #VALUE!
#VALUE! | #VALUE! | #VALUE! | #VALUE! | - | #VALUE! | 1.5838 |  | #VALUE! | 1.2 | 1 | 3300 | 1.2 | 20.83 | 1 | 50 | 1 | 1 | 1 | 0 | 0.75 | - | #VALUE!
#VALUE! | #VALUE! | #VALUE! | #VALUE! | - | #VALUE! | 1.5838 |  | #VALUE! | 1.2 | 1 | 3300 | 1.2 | 20.83 | 1 | 50 | 1 | 1 | 1 | 0 | 0.75 |  | 0
#VALUE! | #VALUE! | #VALUE! | #VALUE! | - | #VALUE! | 1.5838 |  | #VALUE! | 1.2 | 1 | 3300 | 1.2 | 20.83 | 1 | 50 | 1 | 1 | 1 | 0 | 0.75 |  | 0
*Push distances: Assumed 100 feet.

## 7 Ripper
Cobre
Stockpile Worksheet #7
Productivity and Hours Required for | [15 empty] | 2014-12-05
Ripper-Equipped Dozer Use
Note: Scarifying/Ripping Covered Areas Currently Included in Revegetation Costs
PERFORMANCE FACTORS:
[7 empty] | Task | Ripping | Ripper | Pocket | No. of | Turn | Work | Speed | 1000 ft | ripper
Task Description | Location 1 | Location 2 | Equipment | Area | Volume | Productivity | Time | Length | Penetration | Spacing | Pockets | Time | Hour |  |  | path width
|  |  |  | (acres) | (cy) | (acres/hr) | (hours) | (feet) | (in) | (in) |  | (min/pass) | (min/hr) | (mph) | (passes/acre) | (feet)
Rip liners | East WRF Containment | - | D11T w/ ripper | 0.5 | 1210 | 1.7049 | 0.29327 | 1000 | 18 | 69 | 3 | 0.25 | 50 | 1 | 2.5252 | 17.25
Rip liners | Decant Pond #4 | - | D11T w/ ripper | 0.62 | 1500.4 | 1.7049 | 0.36365 | 1000 | 18 | 69 | 3 | 0.25 | 50 | 1 | 2.5252 | 17.25
Rip liners | Blackman's Seep (Pond #2) | - | D11T w/ ripper | 0.01 | 24.2 | 1.7049 | 0.0058654 | 1000 | 18 | 69 | 3 | 0.25 | 50 | 1 | 2.5252 | 17.25
Rip liners | Grape Gulch Pond #3 | - | D11T w/ ripper | 0.38 | 919.6 | 1.7049 | 0.22288 | 1000 | 18 | 69 | 3 | 0.25 | 50 | 1 | 2.5252 | 17.25
Rip liners | Magnetite Seepage Pond | - | D11T w/ ripper | 0.2 | 484 | 1.7049 | 0.11731 | 1000 | 18 | 69 | 3 | 0.25 | 50 | 1 | 2.5252 | 17.25
Rip surface | Reclaim Pond Outlet Channel | - | D11T w/ ripper | 1.7 | 4114 | 1.7049 | 0.99712 | 1000 | 18 | 69 | 3 | 0.25 | 50 | 1 | 2.5252 | 17.25
Rip liners | Upper Creek Containment Pond 1 | - | D11T w/ ripper | 1.13 | 2734.6 | 1.7049 | 0.66279 | 1000 | 18 | 69 | 3 | 0.25 | 50 | 1 | 2.5252 | 17.25

## 8 Excavator
Cobre
Stockpile Worksheet #8
Productivity and Hours Required for Hydraulic Excavator | 2014-12-05
This page intentionally left blank.

## 9 Trucks
[22 empty] | Cobre | [17 empty] | Cobre
[22 empty] | Stockpile Worksheet #9 | [17 empty] | Stockpile Worksheet #9
Productivity and Hours Required for Truck Use | [21 empty] | 2014-12-05 | [17 empty] | 2014-12-05
Truck-Loader Matching
Truck Loading Height (empty), Cat 777F - 14'7"
Loader Dump Clearance, Cat 992G - 15'3"
[9 empty] | PERFORMANCE FACTORS | [13 empty] | Haul | Haul | Haul | Return | Return | Return
[5 empty] | Truck | Optimum |  |  |  |  | Loader | Total | Haul | Haul | Haul | Haul | Haul | Haul |  | Haul | Haul | Haul | Effective | Effective | Effective | Effective | Effective | Effective |  |  |  | Load/ | Dump/ |  | Travel Time | Travel Time | Travel Time | Travel Time | Travel Time | Travel Time
[5 empty] | Cycle | No. of |  | Task | Struck | Heaped | Cycles | Haul | Distance | Distance | Distance | Grade | Grade | Grade | Rolling | Distance | Distance | Distance | Grade | Grade | Grade | Grade | Grade | Grade | Haul | Return | Loading | Maneuver | Maneuver | Work | Loaded | Loaded | Loaded | Empty | Empty | Empty
Task Description | Location 1* | Location 2 | Equipment | Volume | Time | Trucks | Productivity | Time | Capacity | Capacity | per Truck | Distance | Segment 1 | Segment 2 | Segment 3 | Segment 1 | Segment 2 | Segment 3 | Resistance | Segment 1 | Segment 2 | Segment 3 | Segment 1 | Segment 2 | Segment 3 | Segment 1 | Segment 2 | Segment 3 | Time | Time | Time | Time | Time | Hour | Segment 1 | Segment 2 | Segment 3 | Segment 1 | Segment 2 | Segment 3
|  |  |  | (cy) | (min) |  | (cy/hr) | (hrs) | (cy) | (cy) |  | (feet) | (feet) | (feet) | (feet) | (%) | (%) | (%) | (%) | (meters) | (meters) | (meters) | (%) | (%) | (%) | (%) | (%) | (%) | (min) | (min) | (min) | (min) | (min) | (min/hr) | (min/m) | (min/m) | (min/m) | (min/m) | (min/m) | (min/m)
Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | 777F | 412368 | #VALUE! | 2 | 937.6352 | 439.7958 | 54.6 | 78.6 | 5 | 3630 | 3630 | - | - | -0.28% | - | - | 2.5% | 1106.424 | #VALUE! | #VALUE! | 2.22% | #VALUE! | #VALUE! | 2.78% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 3.25 | 0.7 | 1.1 | 50 | 0.0012833 | 0.0009 | 0.0009 | 0.00089996 | 0.0009 | 0.0009
Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | 777F | 1237104 | #VALUE! | 2 | 937.6352 | 1319.3873 | 54.6 | 78.6 | 5 | 3630 | 3630 | - | - | -0.28% | - | - | 2.5% | 1106.424 | #VALUE! | #VALUE! | 2.22% | #VALUE! | #VALUE! | 2.78% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 3.25 | 0.7 | 1.1 | 50 | 0.0012833 | #VALUE! | #VALUE! | 0.00089996 | #VALUE! | #VALUE!
Haul cover soil | NOBS | SWRDF Top | 777F | 119548 | 15.3333 | 4 | 913.0471 | 130.933 | 54.6 | 78.6 | 5 | 12559 | 2310 | 7312 | 2937 | -8.87% | -0.96% | 4.09% | 2.5% | 704.088 | 2228.6976 | 895.1976 | 0% | 1.54% | 6.59% | 11.37% | 3.46% | 0% | 5.7656 | 4.5177 | 3.25 | 0.7 | 1.1 | 50 | 0.0009 | 0.0011244 | 0.0029333 | 0.0023128 | 0.0009349 | 0.0009
Haul cover soil | NOBS | Hanover Mountain Deposit | 777F | 451572 | 11.5025 | 3 | 912.8481 | 494.6847 | 54.6 | 78.6 | 5 | 5707 | 1759 | 2466 | 1482 | -9.95% | -8.11% | 6.75% | 2.5% | 536.1432 | 751.6368 | 451.7136 | 0% | 0% | 9.25% | 12.45% | 10.61% | 0% | 3.0689 | 3.3835 | 3.25 | 0.7 | 1.1 | 50 | 0.0009 | 0.0009 | 0.0042282 | 0.0025625 | 0.0021329 | 0.0009
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | 777F | 57596 | 5.7579 | 2 | 1215.7307 | 53.482 | 54.6 | 78.6 | 5 | 600 | 600 | - | - | 4.17% | - | - | 2.5% | 182.88 | #VALUE! | #VALUE! | 6.67% | #VALUE! | #VALUE! | 0% | #VALUE! | #VALUE! | 0.54326 | 0.16459 | 3.25 | 0.7 | 1.1 | 50 | 0.0029706 | #VALUE! | #VALUE! | 0.0009 | #VALUE! | #VALUE!
Haul cover soil | OB-4 Stockpile | Low Grade WRF | 777F | 44899.0667 | #VALUE! | 2 | 1165.7257 | 41.692 | 54.6 | 78.6 | 5 | 1000 | 1000 | - | - | 2.5% | - | - | 2.5% | 304.8 | #VALUE! | #VALUE! | 5% | #VALUE! | #VALUE! | 0% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 3.25 | 0.7 | 1.1 | 50 | 0.0022327 | #VALUE! | #VALUE! | 0.0009 | #VALUE! | #VALUE!
Haul cover soil | NOBS | MTI Reclaim Pond | 777F | 159720 | 12.1561 | 4 | 1151.6807 | 148.3114 | 54.6 | 78.6 | 5 | 7193 | 2310 | 1940 | 2943 | -8.87% | 1.55% | 3.57% | 2.5% | 704.088 | 591.312 | 897.0264 | 0% | 4.05% | 6.07% | 11.37% | 0.95% | 0% | 4.152 | 2.9542 | 3.25 | 0.7 | 1.1 | 50 | 0.0009 | 0.0018614 | 0.0026952 | 0.0023128 | 0.00087676 | 0.0009
Haul cover soil | NOBS | MTI Top | 777F | 190284.1 | 12.1561 | 4 | 1151.6807 | 176.6924 | 54.6 | 78.6 | 5 | 7193 | 2310 | 1940 | 2943 | -8.87% | 1.55% | 3.57% | 2.5% | 704.088 | 591.312 | 897.0264 | 0% | 4.05% | 6.07% | 11.37% | 0.95% | 0% | 4.152 | 2.9542 | 3.25 | 0.7 | 1.1 | 50 | 0.0009 | 0.0018614 | 0.0026952 | 0.0023128 | 0.00087676 | 0.0009
Haul cover soil | NOBS | MTI Outslope | 777F | 175837.2 | 12.1561 | 4 | 1151.6807 | 163.2774 | 54.6 | 78.6 | 5 | 7193 | 2310 | 1940 | 2943 | -8.87% | 1.55% | 3.57% | 2.5% | 704.088 | 591.312 | 897.0264 | 0% | 4.05% | 6.07% | 11.37% | 0.95% | 0% | 4.152 | 2.9542 | 3.25 | 0.7 | 1.1 | 50 | 0.0009 | 0.0018614 | 0.0026952 | 0.0023128 | 0.00087676 | 0.0009
Haul cover soil | Reclaim Pond Outlet Channel | MTI Top | 777F | 71559.9 | #VALUE! | 2 | 1178.4899 | 66.4485 | 54.6 | 78.6 | 5 | 1172 | 1172 | - | - | 0.85% | - | - | 2.5% | 357.2256 | #VALUE! | #VALUE! | 3.35% | #VALUE! | #VALUE! | 1.65% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 3.25 | 0.7 | 1.1 | 50 | 0.0016167 | #VALUE! | #VALUE! | 0.00087414 | #VALUE! | #VALUE!
Haul cover soil | NOBS | Tailing Pipeline Corridor | 777F | 6998.64 | 12.1561 | 4 | 1151.6807 | 6.4987 | 54.6 | 78.6 | 5 | 7193 | 2310 | 1940 | 2943 | -8.87% | 1.55% | 3.57% | 2.5% | 704.088 | 591.312 | 897.0264 | 0% | 4.05% | 6.07% | 11.37% | 0.95% | 0% | 4.152 | 2.9542 | 3.25 | 0.7 | 1.1 | 50 | 0.0009 | 0.0018614 | 0.0026952 | 0.0023128 | 0.00087676 | 0.0009
Haul cover soil | NOBS | Grape Gulch Pond #3 | 777F | 1839.2 | #VALUE! | 3 | 1206.5715 | 1.7078 | 54.6 | 78.6 | 5 | 3856 | 2310 | 1546 | - | -8.87% | -7.76% | - | 2.5% | 704.088 | 471.2208 | #VALUE! | 0% | 0% | #VALUE! | 11.37% | 10.26% | #VALUE! | #VALUE! | #VALUE! | 3.25 | 0.7 | 1.1 | 50 | 0.0009 | 0.0009 | #VALUE! | 0.0023128 | 0.0020503 | #VALUE!
Haul cover soil | NOBS | Magnetite Seepage Pond | 777F | 968 | 10.4158 | 3 | 1008.0804 | 0.96024 | 54.6 | 78.6 | 5 | 6480 | 2310 | 1940 | 2230 | -8.87% | 1.55% | -4.04% | 2.5% | 704.088 | 591.312 | 679.704 | 0% | 4.05% | 0% | 11.37% | 0.95% | 6.54% | 2.3461 | 3.0198 | 3.25 | 0.7 | 1.1 | 50 | 0.0009 | 0.0018614 | 0.0009 | 0.0023128 | 0.00087676 | 0.0012842
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | 777F | 2516.8 | #VALUE! | 2 | 937.6352 | 2.6842 | 54.6 | 78.6 | 5 | 3630 | 3630 | - | - | -0.28% | - | - | 2.5% | 1106.424 | #VALUE! | #VALUE! | 2.22% | #VALUE! | #VALUE! | 2.78% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 3.25 | 0.7 | 1.1 | 50 | 0.0012833 | #VALUE! | #VALUE! | 0.00089996 | #VALUE! | #VALUE!
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | 777F | 1645.6 | #VALUE! | 2 | 937.6352 | 1.7551 | 54.6 | 78.6 | 5 | 3630 | 3630 | - | - | -0.28% | - | - | 2.5% | 1106.424 | #VALUE! | #VALUE! | 2.22% | #VALUE! | #VALUE! | 2.78% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 3.25 | 0.7 | 1.1 | 50 | 0.0012833 | #VALUE! | #VALUE! | 0.00089996 | #VALUE! | #VALUE!
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | 777F | 4065.6 | #VALUE! | 2 | 937.6352 | 4.336 | 54.6 | 78.6 | 5 | 3630 | 3630 | - | - | -0.28% | - | - | 2.5% | 1106.424 | #VALUE! | #VALUE! | 2.22% | #VALUE! | #VALUE! | 2.78% | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 3.25 | 0.7 | 1.1 | 50 | 0.0012833 | #VALUE! | #VALUE! | 0.00089996 | #VALUE! | #VALUE!
Haul cover soil | OB-4 Stockpile | North Tailings Decant Pond | 777F | 2226.4 | 6.0048 | 2 | 1165.7257 | 2.0674 | 54.6 | 78.6 | 5 | 1000 | 1000 | - | - | 2.5% | - | - | 2.5% | 304.8 | #VALUE! | #VALUE! | 5% | #VALUE! | #VALUE! | 0% | #VALUE! | #VALUE! | 0.68052 | 0.27432 | 3.25 | 0.7 | 1.1 | 50 | 0.0022327 | #VALUE! | #VALUE! | 0.0009 | #VALUE! | #VALUE!
Haul cover soil | OB-4 Stockpile | East WRF Containment | 777F | 2420 | 6.0048 | 2 | 1165.7257 | 2.2471 | 54.6 | 78.6 | 5 | 1000 | 1000 | - | - | 2.5% | - | - | 2.5% | 304.8 | #VALUE! | #VALUE! | 5% | #VALUE! | #VALUE! | 0% | #VALUE! | #VALUE! | 0.68052 | 0.27432 | 3.25 | 0.7 | 1.1 | 50 | 0.0022327 | #VALUE! | #VALUE! | 0.0009 | #VALUE! | #VALUE!
Haul cover soil | NOBS | Blackman's Seep (Pond #2) | 777F | 48.4 | 8.7023 | 3 | 1206.5715 | 0.044943 | 54.6 | 78.6 | 5 | 3856 | 2310 | 1546 | - | -8.87% | -7.76% | - | 2.5% | 704.088 | 471.2208 | #VALUE! | 0% | 0% | #VALUE! | 11.37% | 10.26% | #VALUE! | 1.0578 | 2.5946 | 3.25 | 0.7 | 1.1 | 50 | 0.0009 | 0.0009 | #VALUE! | 0.0023128 | 0.0020503 | #VALUE!
Haul cover soil | OB-4 Stockpile | Decant Pond #4 | 777F | 3000.8 | 6.0048 | 2 | 1165.7257 | 2.7865 | 54.6 | 78.6 | 5 | 1000 | 1000 | - | - | 2.5% | - | - | 2.5% | 304.8 | #VALUE! | #VALUE! | 5% | #VALUE! | #VALUE! | 0% | #VALUE! | #VALUE! | 0.68052 | 0.27432 | 3.25 | 0.7 | 1.1 | 50 | 0.0022327 | #VALUE! | #VALUE! | 0.0009 | #VALUE! | #VALUE!
Haul cover soil | NOBS | Upper Creek Containment Pond 1 | 777F | 5469.2 | 8.7023 | 3 | 1206.5715 | 5.0785 | 54.6 | 78.6 | 5 | 3856 | 2310 | 1546 | - | -8.87% | -7.76% | - | 2.5% | 704.088 | 471.2208 | #VALUE! | 0% | 0% | #VALUE! | 11.37% | 10.26% | #VALUE! | 1.0578 | 2.5946 | 3.25 | 0.7 | 1.1 | 50 | 0.0009 | 0.0009 | #VALUE! | 0.0023128 | 0.0020503 | #VALUE!
*Cover material is assumed to be obtained for each facility based on the 2014 mine expansion plan, the volume of available cover material, and proximity to the facility being covered. These haul routes are subject to change based on those factors.

## 10 Loader
Cobre
Stockpile Worksheet #10
Productivity for Front End Loader | [10 empty] | 2014-12-05
PERFORMANCE FACTORS
[5 empty] | Net | Loader |  |  | Rated | Bucket
[5 empty] | Bucket | Cycle |  | Task | Bucket | Fill | Work
Task Description | Location 1 | Location 2 | Equipment | Volume | Capacity | Time | Productivity | Time | Capacity | Factor | Hour
|  |  |  | (cy) | (cy) | (min) | (cy/hr) | (hours) | (cy) |  | (min/hr)
Load cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | 992K | 412368 | 14 | 0.65 | 1076.9231 | 382.9131 | 16 | 0.875 | 50
Load cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | 992K | 1237104 | 14 | 0.65 | 1076.9231 | 1148.7394 | 16 | 0.875 | 50
Load cover soil | NOBS | SWRDF Top | 992K | 119548 | 14 | 0.65 | 1076.9231 | 111.0089 | 16 | 0.875 | 50
Load cover soil | NOBS | Hanover Mountain Deposit | 992K | 451572 | 14 | 0.65 | 1076.9231 | 419.3169 | 16 | 0.875 | 50
Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | 992K | 57596 | 14 | 0.65 | 1076.9231 | 53.482 | 16 | 0.875 | 50
Load cover soil | OB-4 Stockpile | Low Grade WRF | 992K | 44899.0667 | 14 | 0.65 | 1076.9231 | 41.692 | 16 | 0.875 | 50
Load cover soil | NOBS | MTI Reclaim Pond | 992K | 159720 | 14 | 0.65 | 1076.9231 | 148.3114 | 16 | 0.875 | 50
Load cover soil | NOBS | MTI Top | 992K | 190284.1 | 14 | 0.65 | 1076.9231 | 176.6924 | 16 | 0.875 | 50
Load cover soil | NOBS | MTI Outslope | 992K | 175837.2 | 14 | 0.65 | 1076.9231 | 163.2774 | 16 | 0.875 | 50
Load cover soil | Reclaim Pond Outlet Channel | MTI Top | 992K | 71559.9 | 14 | 0.65 | 1076.9231 | 66.4485 | 16 | 0.875 | 50
Load cover soil | NOBS | Tailing Pipeline Corridor | 992K | 6998.64 | 14 | 0.65 | 1076.9231 | 6.4987 | 16 | 0.875 | 50
Load cover soil | NOBS | Grape Gulch Pond #3 | 992K | 1839.2 | 14 | 0.65 | 1076.9231 | 1.7078 | 16 | 0.875 | 50
Load cover soil | NOBS | Magnetite Seepage Pond | 992K | 968 | 14 | 0.65 | 1076.9231 | 0.89886 | 16 | 0.875 | 50
Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | 992K | 2516.8 | 14 | 0.65 | 1076.9231 | 2.337 | 16 | 0.875 | 50
Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | 992K | 1645.6 | 14 | 0.65 | 1076.9231 | 1.5281 | 16 | 0.875 | 50
Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | 992K | 4065.6 | 14 | 0.65 | 1076.9231 | 3.7752 | 16 | 0.875 | 50
Load cover soil | OB-4 Stockpile | North Tailings Decant Pond | 992K | 2226.4 | 14 | 0.65 | 1076.9231 | 2.0674 | 16 | 0.875 | 50
Load cover soil | OB-4 Stockpile | East WRF Containment | 992K | 2420 | 14 | 0.65 | 1076.9231 | 2.2471 | 16 | 0.875 | 50
Load cover soil | NOBS | Blackman's Seep (Pond #2) | 992K | 48.4 | 14 | 0.65 | 1076.9231 | 0.044943 | 16 | 0.875 | 50
Load cover soil | OB-4 Stockpile | Decant Pond #4 | 992K | 3000.8 | 14 | 0.65 | 1076.9231 | 2.7865 | 16 | 0.875 | 50
Load cover soil | NOBS | Upper Creek Containment Pond 1 | 992K | 5469.2 | 14 | 0.65 | 1076.9231 | 5.0785 | 16 | 0.875 | 50

## 11 Scraper
Cobre
Stockpile Worksheet #11
Productivity and Hours Required for Scraper Use | 2014-12-05
This page intentionally left blank.

## 12 M'grader
Cobre
Stockpile Worksheet #12
Productivity and Hours Required for Motor grader Use---Grading | 2014-12-05
This page intentionally left blank.

## 13 EarthSum
Cobre
Stockpile Worksheet #13
Summary Calculation of Earthmoving Costs | [11 empty] | 2014-12-05
Equipment |  |  |  |  | Owning and | Labor | Number of | Time | Direct | Total | Prod. | Unit | Total | Fleet |  |  | Total | Fleet
Type |  | Task | Location 1 | Location 2 | Operating Cost | Cost | Units | Req'd | Cost | Production | Unit | Cost | Unit Cost | Production |  |  | Unit Cost | Production
[5 empty] | ($/hr) | ($/hr) | (Equipment) | (hrs) | ($) |  |  | ($/unit) | ($/unit) | (cy/hr) |  |  | ($/ton) | (ton/hr)
Dozers-Earthmoving
| D11T CD | Regrade Top | SWRDF | Top | 509.12 | 47.58 | 1 | 1486.2316 | 827385.1577 | 666680 | cy | 1.2411 | 1.2411 | 448.5707 |  |  | 0.75215 | 740.1417
| D11T CD | Regrade Top | MTI | Top | 509.12 | 47.58 | 1 | 42.4414 | 23627.1321 | 50794.5 | cy | 0.46515 | 0.46515 | 1196.8147 |  |  | 0.28191 | 1974.7442
| D11T CD | Regrade Outslope | MTI Reclaim Pond | Top and Outslope | 509.12 | 47.58 | 1 | 39.4116 | 21940.4118 | 67765 | cy | 0.32377 | 0.32377 | 1719.4197 |  |  | 0.22329 | 2493.1585
| D11T CD | Regrade Outslope | MTI | Outslope | 509.12 | 47.58 | 1 | 105.5078 | 58736.1913 | 170294 | cy | 0.34491 | 0.34491 | 1614.0418 |  |  | 0.23787 | 2340.3607
| D11T CD | Dozer Assist | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | 509.12 | 47.58 | 1 | 382.9131 | 213167.7466 | 412368 | cy | 0.51694 | 1.9715 | 937.6352 |  | Cover -> | 1.1949 | 1547.0981
| D11T CD | Dozer Assist | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | 509.12 | 47.58 | 1 | 1148.7394 | 639503.2399 | 1237104 | cy | 0.51694 | 1.8653 | 937.6352 |  | Cover -> | 1.1305 | 1547.0981
| D11T CD | Dozer Assist | NOBS | SWRDF Top | 509.12 | 47.58 | 1 | 111.0089 | 61798.6308 | 119548 | cy | 0.51694 | 2.7416 | 913.0471 |  | Cover -> | 1.6616 | 1506.5277
| D11T CD | Dozer Assist | NOBS | Hanover Mountain Deposit | 509.12 | 47.58 | 1 | 419.3169 | 233433.6944 | 451572 | cy | 0.51694 | 2.3726 | 912.8481 |  | Cover -> | 1.4379 | 1506.1994
| D11T CD | Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | 509.12 | 47.58 | 1 | 53.482 | 29773.4294 | 57596 | cy | 0.51694 | 1.979 | 1076.9231 |  | Cover -> | 1.1994 | 1776.9231
| D11T CD | Dozer Assist | OB-4 Stockpile | Low Grade WRF | 509.12 | 47.58 | 1 | 41.692 | 23209.9311 | 44899.0667 | cy | 0.51694 | 1.7092 | 1076.9231 |  | Cover -> | 1.0359 | 1776.9231
| D11T CD | Dozer Assist | NOBS | MTI Reclaim Pond | 509.12 | 47.58 | 1 | 148.3114 | 82564.9723 | 159720 | cy | 0.51694 | 2.3354 | 1076.9231 |  | Cover -> | 1.4154 | 1776.9231
| D11T CD | Dozer Assist | NOBS | MTI Top | 509.12 | 47.58 | 1 | 176.6924 | 98364.6472 | 190284.1 | cy | 0.51694 | 2.4485 | 1076.9231 |  | Cover -> | 1.4839 | 1776.9231
| D11T CD | Dozer Assist | NOBS | MTI Outslope | 509.12 | 47.58 | 1 | 163.2774 | 90896.5286 | 175837.2 | cy | 0.51694 | 2.3354 | 1076.9231 |  | Cover -> | 1.4154 | 1776.9231
| D11T CD | Dozer Assist | Reclaim Pond Outlet Channel | MTI Top | 509.12 | 47.58 | 1 | 66.4485 | 36991.868 | 62226 | cy | 0.59448 | 2.0408 | 936.4548 |  | Cover -> | 1.2369 | 1545.1505
| D11T CD | Dozer Assist | NOBS | Tailing Pipeline Corridor | 509.12 | 47.58 | 1 | 6.4987 | 3617.847 | 6998.64 | cy | 0.51694 | 2.4472 | 1076.9231 |  | Cover -> | 1.4831 | 1776.9231
| D11T CD | Dozer Assist | NOBS | Grape Gulch Pond #3 | 509.12 | 47.58 | 1 | 1.7078 | 950.7482 | 1839.2 | cy | 0.51694 | 2.2751 | 1076.9231 |  | Cover -> | 1.3789 | 1776.9231
| D11T CD | Dozer Assist | NOBS | Magnetite Seepage Pond | 509.12 | 47.58 | 1 | 0.89886 | 500.3938 | 968 | cy | 0.51694 | 2.3658 | 1008.0804 |  | Cover -> | 1.4338 | 1663.3327
| D11T CD | Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | 509.12 | 47.58 | 1 | 2.337 | 1301.0238 | 2516.8 | cy | 0.51694 | 1.9715 | 937.6352 |  | Cover -> | 1.1949 | 1547.0981
| D11T CD | Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | 509.12 | 47.58 | 1 | 1.5281 | 850.6694 | 1645.6 | cy | 0.51694 | 1.9715 | 937.6352 |  | Cover -> | 1.1949 | 1547.0981
| D11T CD | Dozer Assist | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | 509.12 | 47.58 | 1 | 3.7752 | 2101.6538 | 4065.6 | cy | 0.51694 | 1.9715 | 937.6352 |  | Cover -> | 1.1949 | 1547.0981
| D11T CD | Dozer Assist | OB-4 Stockpile | North Tailings Decant Pond | 509.12 | 47.58 | 1 | 2.0674 | 1150.9057 | 2226.4 | cy | 0.51694 | 1.8209 | 1076.9231 |  | Cover -> | 1.1036 | 1776.9231
| D11T CD | Dozer Assist | OB-4 Stockpile | East WRF Containment | 509.12 | 47.58 | 1 | 2.2471 | 1250.9844 | 2420 | cy | 0.51694 | 1.962 | 1076.9231 |  | Cover -> | 1.1891 | 1776.9231
| D11T CD | Dozer Assist | NOBS | Blackman's Seep (Pond #2) | 509.12 | 47.58 | 1 | 0.044943 | 25.0197 | 48.4 | cy | 0.51694 | 2.2751 | 1076.9231 |  | Cover -> | 1.3789 | 1776.9231
| D11T CD | Dozer Assist | OB-4 Stockpile | Decant Pond #4 | 509.12 | 47.58 | 1 | 2.7865 | 1551.2207 | 3000.8 | cy | 0.51694 | 1.962 | 1076.9231 |  | Cover -> | 1.1891 | 1776.9231
| D11T CD | Dozer Assist | NOBS | Upper Creek Containment Pond 1 | 509.12 | 47.58 | 1 | 5.0785 | 2827.2248 | 5469.2 | cy | 0.51694 | 2.2751 | 1076.9231 |  | Cover -> | 1.3789 | 1776.9231
Dozers-Grading
| 16M | Grade surface | Haul Roads | - | 509.12 | 47.58 | 1 | 14.5061 | 8075.5315 | 45 | ac | 179.4563
| 16M | Grade surface | Exploration Roads | - | 509.12 | 47.58 | 1 | 11.9272 | 6639.8814 | 37 | ac | 179.4563
| 16M | Grade surface | Low Grade WRF | - | 509.12 | 47.58 | 1 | 8.9712 | 4994.2676 | 27.83 | ac | 179.4563
| 16M | Grade surface | Grape Gulch Pond #3 | - | 509.12 | 47.58 | 1 | 0.1225 | 68.1934 | 0.38 | ac | 179.4563
| 16M | Grade surface | Magnetite Seepage Pond | - | 509.12 | 47.58 | 1 | 0.064471 | 35.8913 | 0.2 | ac | 179.4563
| 16M | Grade surface | SWRF Dam 1 | - | 509.12 | 47.58 | 1 | 0.16763 | 93.3173 | 0.52 | ac | 179.4563
| 16M | Grade surface | SWRF Dam 2 | - | 509.12 | 47.58 | 1 | 0.1096 | 61.0151 | 0.34 | ac | 179.4563
| 16M | Grade surface | SWRF Dam 3 | - | 509.12 | 47.58 | 1 | 0.27078 | 150.7433 | 0.84 | ac | 179.4563
| 16M | Grade surface | North Tailings Decant Pond | - | 509.12 | 47.58 | 1 | 0.14828 | 82.5499 | 0.46 | ac | 179.4563
| 16M | Grade surface | East WRF Containment | - | 509.12 | 47.58 | 1 | 0.16118 | 89.7281 | 0.5 | ac | 179.4563
| 16M | Grade surface | Blackman's Seep (Pond #2) | - | 509.12 | 47.58 | 1 | 0.0032236 | 1.7946 | 0.01 | ac | 179.4563
| 16M | Grade surface | Decant Pond #4 | - | 509.12 | 47.58 | 1 | 0.19986 | 111.2629 | 0.62 | ac | 179.4563
| 16M | Grade surface | Upper Creek Containment Pond 1 | - | 509.12 | 47.58 | 1 | 0.36426 | 202.7856 | 1.13 | ac | 179.4563
| D11T CD | Grade cover soil | SWRDF Top | - | 509.12 | 47.58 | 1 | 214.6734 | 119508.7085 | 412368 | cy | 0.28981
| D11T CD | Grade cover soil | SWRDF Outslopes | - | 509.12 | 47.58 | 1 | 408.0129 | 227140.7752 | 1237104 | cy | 0.18361
| D11T CD | Grade cover soil | SWRDF Top | - | 509.12 | 47.58 | 1 | 62.2351 | 34646.304 | 119548 | cy | 0.28981
| D11T CD | Grade cover soil | Hanover Mountain Deposit | - | 509.12 | 47.58 | 1 | 235.0825 | 130870.4519 | 451572 | cy | 0.28981
| D11T CD | Grade cover soil | Pearson-Barnes Mine Area | - | 509.12 | 47.58 | 1 | 46.3385 | 25796.6408 | 57596 | cy | 0.44789
| D11T CD | Grade cover soil | Low Grade WRF | - | 509.12 | 47.58 | 1 | 14.3623 | 7995.4699 | 44899.0667 | cy | 0.17808
| D11T CD | Grade cover soil | MTI Reclaim Pond | - | 509.12 | 47.58 | 1 | 51.091 | 28442.3831 | 159720 | cy | 0.17808
| D11T CD | Grade cover soil | MTI Top | - | 509.12 | 47.58 | 1 | 99.5082 | 55396.2173 | 190284.1 | cy | 0.29112
| D11T CD | Grade cover soil | MTI Outslope | - | 509.12 | 47.58 | 1 | 56.2466 | 31312.4781 | 175837.2 | cy | 0.17808
| D11T CD | Grade cover soil | MTI Top | - | 509.12 | 47.58 | 1 | 37.4219 | 20832.7851 | 71559.9 | cy | 0.29112
| D11T CD | Grade cover soil | Tailing Pipeline Corridor | - | 509.12 | 47.58 | 1 | 3.6434 | 2028.2816 | 6998.64 | cy | 0.28981
| D11T CD | Grade cover soil | Grape Gulch Pond #3 | - | 509.12 | 47.58 | 1 | 0.95746 | 533.0201 | 1839.2 | cy | 0.28981
| D11T CD | Grade cover soil | Magnetite Seepage Pond | - | 509.12 | 47.58 | 1 | 0.50393 | 280.5369 | 968 | cy | 0.28981
| D11T CD | Grade cover soil | SWRF Dam 1 | - | 509.12 | 47.58 | 1 | 1.3102 | 729.3959 | 2516.8 | cy | 0.28981
| D11T CD | Grade cover soil | SWRF Dam 2 | - | 509.12 | 47.58 | 1 | 0.85668 | 476.9127 | 1645.6 | cy | 0.28981
| D11T CD | Grade cover soil | SWRF Dam 3 | - | 509.12 | 47.58 | 1 | 2.1165 | 1178.2549 | 4065.6 | cy | 0.28981
| D11T CD | Grade cover soil | North Tailings Decant Pond | - | 509.12 | 47.58 | 1 | 1.159 | 645.2348 | 2226.4 | cy | 0.28981
| D11T CD | Grade cover soil | East WRF Containment | - | 509.12 | 47.58 | 1 | 1.2598 | 701.3422 | 2420 | cy | 0.28981
| D11T CD | Grade cover soil | Blackman's Seep (Pond #2) | - | 509.12 | 47.58 | 1 | 0.025196 | 14.0268 | 48.4 | cy | 0.28981
| D11T CD | Grade cover soil | Decant Pond #4 | - | 509.12 | 47.58 | 1 | 1.5622 | 869.6643 | 3000.8 | cy | 0.28981
| D11T CD | Grade cover soil | Upper Creek Containment Pond 1 | - | 509.12 | 47.58 | 1 | 2.8472 | 1585.0333 | 5469.2 | cy | 0.28981
Loaders
| 992K | Load cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | 369.97 | 47.75 | 1 | 439.7958 | 183711.4864 | 412368 | cy | 0.4455
| 992K | Load cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | 369.97 | 47.75 | 1 | 1319.3873 | 551134.4592 | 1237104 | cy | 0.4455
| 992K | Load cover soil | NOBS | SWRDF Top | 369.97 | 47.75 | 1 | 130.933 | 54693.3359 | 119548 | cy | 0.4575
| 992K | Load cover soil | NOBS | Hanover Mountain Deposit | 369.97 | 47.75 | 1 | 494.6847 | 206639.6877 | 451572 | cy | 0.4576
| 992K | Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | 369.97 | 47.75 | 1 | 53.482 | 22340.501 | 57596 | cy | 0.38788
| 992K | Load cover soil | OB-4 Stockpile | Low Grade WRF | 369.97 | 47.75 | 1 | 41.692 | 17415.5783 | 44899.0667 | cy | 0.38788
| 992K | Load cover soil | NOBS | MTI Reclaim Pond | 369.97 | 47.75 | 1 | 148.3114 | 61952.6499 | 159720 | cy | 0.38788
| 992K | Load cover soil | NOBS | MTI Top | 369.97 | 47.75 | 1 | 176.6924 | 73807.9404 | 190284.1 | cy | 0.38788
| 992K | Load cover soil | NOBS | MTI Outslope | 369.97 | 47.75 | 1 | 163.2774 | 68204.2355 | 175837.2 | cy | 0.38788
| 992K | Load cover soil | Reclaim Pond Outlet Channel | MTI Top | 369.97 | 47.75 | 1 | 66.4485 | 27756.8585 | 71559.9 | cy | 0.38788
| 992K | Load cover soil | NOBS | Tailing Pipeline Corridor | 369.97 | 47.75 | 1 | 6.4987 | 2714.6525 | 6998.64 | cy | 0.38788
| 992K | Load cover soil | NOBS | Grape Gulch Pond #3 | 369.97 | 47.75 | 1 | 1.7078 | 713.3942 | 1839.2 | cy | 0.38788
| 992K | Load cover soil | NOBS | Magnetite Seepage Pond | 369.97 | 47.75 | 1 | 0.96024 | 401.1118 | 968 | cy | 0.41437
| 992K | Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | 369.97 | 47.75 | 1 | 2.6842 | 1121.2438 | 2516.8 | cy | 0.4455
| 992K | Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | 369.97 | 47.75 | 1 | 1.7551 | 733.121 | 1645.6 | cy | 0.4455
| 992K | Load cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | 369.97 | 47.75 | 1 | 4.336 | 1811.24 | 4065.6 | cy | 0.4455
| 992K | Load cover soil | OB-4 Stockpile | North Tailings Decant Pond | 369.97 | 47.75 | 1 | 2.0674 | 863.5824 | 2226.4 | cy | 0.38788
| 992K | Load cover soil | OB-4 Stockpile | East WRF Containment | 369.97 | 47.75 | 1 | 2.2471 | 938.6765 | 2420 | cy | 0.38788
| 992K | Load cover soil | NOBS | Blackman's Seep (Pond #2) | 369.97 | 47.75 | 1 | 0.044943 | 18.7735 | 48.4 | cy | 0.38788
| 992K | Load cover soil | OB-4 Stockpile | Decant Pond #4 | 369.97 | 47.75 | 1 | 2.7865 | 1163.9589 | 3000.8 | cy | 0.38788
| 992K | Load cover soil | NOBS | Upper Creek Containment Pond 1 | 369.97 | 47.75 | 1 | 5.0785 | 2121.4089 | 5469.2 | cy | 0.38788
Trucks
| 777F | Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | 294.4 | 42.82 | 2 | 439.7958 | 296615.8549 | 412368 | cy | 0.7193
| 777F | Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | 294.4 | 42.82 | 2 | 1319.3873 | 889847.5646 | 1237104 | cy | 0.7193
| 777F | Haul cover soil | NOBS | SWRDF Top | 294.4 | 42.82 | 4 | 130.933 | 176612.915 | 119548 | cy | 1.4773
| 777F | Haul cover soil | NOBS | Hanover Mountain Deposit | 294.4 | 42.82 | 3 | 494.6847 | 500452.7111 | 451572 | cy | 1.1082
| 777F | Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | 294.4 | 42.82 | 2 | 53.482 | 36070.4001 | 57596 | cy | 0.62627
| 777F | Haul cover soil | OB-4 Stockpile | Low Grade WRF | 294.4 | 42.82 | 2 | 41.692 | 28118.7461 | 44899.0667 | cy | 0.62627
| 777F | Haul cover soil | NOBS | MTI Reclaim Pond | 294.4 | 42.82 | 4 | 148.3114 | 200054.3198 | 159720 | cy | 1.2525
| 777F | Haul cover soil | NOBS | MTI Top | 294.4 | 42.82 | 4 | 176.6924 | 238336.8156 | 190284.1 | cy | 1.2525
| 777F | Haul cover soil | NOBS | MTI Outslope | 294.4 | 42.82 | 4 | 163.2774 | 220241.6193 | 175837.2 | cy | 1.2525
| 777F | Haul cover soil | Reclaim Pond Outlet Channel | MTI Top | 294.4 | 42.82 | 2 | 66.4485 | 44815.5119 | 71559.9 | cy | 0.62627
| 777F | Haul cover soil | NOBS | Tailing Pipeline Corridor | 294.4 | 42.82 | 4 | 6.4987 | 8766.0166 | 6998.64 | cy | 1.2525
| 777F | Haul cover soil | NOBS | Grape Gulch Pond #3 | 294.4 | 42.82 | 3 | 1.7078 | 1727.7419 | 1839.2 | cy | 0.9394
| 777F | Haul cover soil | NOBS | Magnetite Seepage Pond | 294.4 | 42.82 | 3 | 0.96024 | 971.4372 | 968 | cy | 1.0036
| 777F | Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | 294.4 | 42.82 | 2 | 2.6842 | 1810.3315 | 2516.8 | cy | 0.7193
| 777F | Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | 294.4 | 42.82 | 2 | 1.7551 | 1183.6783 | 1645.6 | cy | 0.7193
| 777F | Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | 294.4 | 42.82 | 2 | 4.336 | 2924.3817 | 4065.6 | cy | 0.7193
| 777F | Haul cover soil | OB-4 Stockpile | North Tailings Decant Pond | 294.4 | 42.82 | 2 | 2.0674 | 1394.318 | 2226.4 | cy | 0.62627
| 777F | Haul cover soil | OB-4 Stockpile | East WRF Containment | 294.4 | 42.82 | 2 | 2.2471 | 1515.563 | 2420 | cy | 0.62627
| 777F | Haul cover soil | NOBS | Blackman's Seep (Pond #2) | 294.4 | 42.82 | 3 | 0.044943 | 45.4669 | 48.4 | cy | 0.9394
| 777F | Haul cover soil | OB-4 Stockpile | Decant Pond #4 | 294.4 | 42.82 | 2 | 2.7865 | 1879.2982 | 3000.8 | cy | 0.62627
| 777F | Haul cover soil | NOBS | Upper Creek Containment Pond 1 | 294.4 | 42.82 | 3 | 5.0785 | 5137.7587 | 5469.2 | cy | 0.9394
Rippers
| D11T w/ ripper | Rip liners | East WRF Containment | - | 534.56 | 47.58 | 1 | 0.29327 | 170.7239 | 1210 | cy | 0.14109
| D11T w/ ripper | Rip liners | Decant Pond #4 | - | 534.56 | 47.58 | 1 | 0.36365 | 211.6977 | 1500.4 | cy | 0.14109
| D11T w/ ripper | Rip liners | Blackman's Seep (Pond #2) | - | 534.56 | 47.58 | 1 | 0.0058654 | 3.4145 | 24.2 | cy | 0.14109
| D11T w/ ripper | Rip liners | Grape Gulch Pond #3 | - | 534.56 | 47.58 | 1 | 0.22288 | 129.7502 | 919.6 | cy | 0.14109
| D11T w/ ripper | Rip liners | Magnetite Seepage Pond | - | 534.56 | 47.58 | 1 | 0.11731 | 68.2896 | 484 | cy | 0.14109
| D11T w/ ripper | Rip surface | Reclaim Pond Outlet Channel | - | 534.56 | 47.58 | 1 | 0.99712 | 580.4614 | 4114 | cy | 0.14109
| D11T w/ ripper | Rip liners | Upper Creek Containment Pond 1 | - | 534.56 | 47.58 | 1 | 0.66279 | 385.8361 | 2734.6 | cy | 0.14109
Water Truck and Grader
| Off-Hwy Water Tanker Truck | SWRDF |  |  | 171.97 | 25.34 | 1 | 1890.1161 | 372938.8002
| Off-Hwy Water Tanker Truck | Hanover Mountain Deposit |  |  | 171.97 | 25.34 | 1 | 494.6847 | 97606.2357
| Off-Hwy Water Tanker Truck | Pearson-Barnes Mine Area |  |  | 171.97 | 25.34 | 1 | 53.482 | 10552.5334
| Off-Hwy Water Tanker Truck | Low Grade WRF |  |  | 171.97 | 25.34 | 1 | 41.692 | 8226.2466
| Off-Hwy Water Tanker Truck | MTI |  |  | 171.97 | 25.34 | 1 | 561.2284 | 8226.2466
| Off-Hwy Water Tanker Truck | Surface Impoundments |  |  | 171.97 | 25.34 | 1 | 23.6678 | 4669.8925
| Motor Grader | SWRDF |  |  | 164.06 | 47.58 | 1 | 1890.1161 | 400024.1634
| Motor Grader | Hanover Mountain Deposit |  |  | 164.06 | 47.58 | 1 | 494.6847 | 104695.0673
| Motor Grader | Pearson-Barnes Mine Area |  |  | 164.06 | 47.58 | 1 | 53.482 | 11318.9305
| Motor Grader | Low Grade WRF |  |  | 164.06 | 47.58 | 1 | 41.692 | 8823.6929
| Motor Grader | MTI |  |  | 164.06 | 47.58 | 1 | 561.2284 | 118778.3834
| Motor Grader | Surface Impoundments |  |  | 164.06 | 47.58 | 1 | 23.6678 | 5009.052
[8 empty] | SWRDF | 5048729.1425
[8 empty] | Hanover Mountain Deposit | 1273697.8481
[8 empty] | Pearson-Barnes Mine Area | 135852.4352
[8 empty] | Low Grade WRF | 98783.9324
[8 empty] | MTI | 1628987.4549
[8 empty] | Haul and Exploration Roads | 14715.4129
[8 empty] | Surface Impoundments | 59545.6901
[8 empty] | Earthwork Direct Cost | 8260311.9161 |  |  |  | Q/A Check -> |  | 8260311.9161
Fuel-
[6 empty] | Owning and | Adjusted
|  | EQUIPMENT |  | Fuel | Fuel | Operating Cost | Own/Op
|  |  |  | Consumption | Cost | (w/out fuel) | Cost
|  | Equipment Description |  | (gal/hr) | ($/hr) | ($/hr) | ($/hr) | Reference
|  | Cat D11T CD Bulldozer |  | 29.7512 | 95.65 | 413.47 | 509.12 | 1
|  | Cat D11T Bulldozer w/ multi shank ripper |  | 29.7512 | 95.65 | 438.91 | 534.56 | 1
|  | Cat 777F Truck |  | 18.7589 | 60.31 | 234.09 | 294.4 | 1
|  | Cat 992K Loader |  | 25.633 | 82.41 | 287.56 | 369.97 | 1
|  | Cat 16M Motor Grader |  | 9.5054 | 30.56 | 133.5 | 164.06 | 1
|  | Off-Hwy Water Tanker Truck, 10,000-gal. |  | 15.3437 | 49.33 | 122.64 | 171.97 | 1
FUEL
|  | Oil Broker Quote |  |  |  | 3.215 | per gallon | 2
Nominal
|  | LABOR |  |  |  |  | Total
|  |  |  | NMDOL Type A | NMDOL Type A |  | Rate
|  | Labor Description |  | Operator Group | Operator Classification |  | ($/hr)
|  | Cat D11T CD Bulldozer |  | Equipment Operator IV | Bulldozer (mult. Units) |  | 47.58 | 3
|  | Cat D11T Bulldozer w/ multi shank ripper |  | Equipment Operator IV | Bulldozer (mult. Units) |  | 47.58
|  | Cat 777F Truck |  | Truck Driver III | Haul Truck |  | 42.82 | 3
|  | Cat 992K Loader |  | Equipment Operator VI | Loader (over 10 cy) |  | 47.75 | 3
|  | Cat 16M Motor Grader |  | Equipment Operator IV | Motor Grader |  | 47.58 | 3
|  | Off-Hwy Water Tanker Truck, 10,000-gal. |  | N/A | N/A |  | 25.34 | 3
References
1. Equipment unit rates from EquipmentWatch Custom Cost Evaluator Version 6.15.0B (http://www.equipmentwatch.com). See attachments for rate development.
2. Western Refining Quote, Lordsburg NM (June 18, 2014).
3. Labor rates based on NM Department of Labor Type H (Heavy Engineering) labor rates. See attachments for rate development.

## 14 Reveg
Cobre
Stockpile Worksheet #14
Revegetation Costs |  |  |  | 2014-12-05
Description:
Chiseling or ripping, scarifying, disking, rangeland drill seeding, mulching, crimping, mobilization.
|  |  | Unit | Direct
|  |  | Cost | Cost
| Unit or Disturbance | (acres) | ($/acre) | ($)
| SWRDF Top | 85.2 | 898.675 | 76567.1083
| SWRDF Outslopes | 255.6 | 898.675 | 229701.325
| SWRDF Top | 24.7 | 898.675 | 22197.272
| Hanover Mountain Deposit | 93.3 | 898.675 | 83846.3757
| Pearson-Barnes Mine Area | 11.9 | 898.675 | 10694.2323
| Low Grade WRF | 27.83 | 898.675 | 25010.1247
| MTI Reclaim Pond | 33 | 898.675 | 29656.2744
| MTI Outslope | 36.33 | 898.675 | 32648.862
| MTI Top | 108.2 | 898.675 | 97236.6329
| Tailing Pipeline Corridor | 1.446 | 898.675 | 1299.484
| Haul Roads | 45 | 898.675 | 40440.3741
| Exploration Roads | 37 | 898.675 | 33250.9743
| Continental Pit berm and fence disturbance | 17.6 | 898.675 | 15816.6797
| Disturbed Area Adjacent and North of the SWRDF | 20.9 | 898.675 | 18782.3071
Surface Impoundments
| Grape Gulch Pond #3 | 0.38 | 898.675 | 341.4965
| Magnetite Seepage Pond | 0.2 | 898.675 | 179.735
| SWRF Dam 1 | 0.52 | 898.675 | 467.311
| SWRF Dam 2 | 0.34 | 898.675 | 305.5495
| SWRF Dam 3 | 0.84 | 898.675 | 754.887
| North Tailings Decant Pond | 0.46 | 898.675 | 413.3905
| East WRF Containment | 0.5 | 898.675 | 449.3375
| Blackman's Seep (Pond #2) | 0.01 | 898.675 | 8.9867
| Decant Pond #4 | 0.62 | 898.675 | 557.1785
| Upper Creek Containment Pond 1 | 1.13 | 898.675 | 1015.5027
Borrow Areas
| Top Soil Stockpile | 0.22483 | 898.675 | 202.0533
| NOBS (proposed) | 17.366 | 898.675 | 15606.3897
| South OB Stockpile (proposed) | 18.3 | 898.675 | 16445.7521
| Reclaim Pond Outlet Channel | 1.7 | 898.675 | 1527.7475
| OB Stockpile-1 | 4.6231 | 898.675 | 4154.6801
| OB Stockpile-2 | 0.91 | 898.675 | 817.7942
| OB Stockpile-3 | 5.036 | 898.675 | 4525.7252
| OB Stockpile-4 | 4.264 | 898.675 | 3831.9501
| OB Stockpile-5 | 3.346 | 898.675 | 3006.9665
|  |  | SWRDF | 376400.9839
|  |  | Hanover Mountain Deposit | 99452.7654
|  |  | Pearson-Barnes Mine Area | 10694.2323
|  |  | Low Grade WRF | 28842.0748
|  |  | MTI | 162369.0008
|  |  | Haul and Exploration Roads | 73691.3484
|  |  | Surface Impoundments | 4493.3749
|  |  | Continental Pit | 15816.6797
|  |  | Revegetation Direct Cost | 771760.4602
*Rocky Mountain Reclamation Quote June, 18 2014, $1153/acre minus 28.3% indirect costs. Quote includes cost for scarifying (ripping) surface.
|  |  |  | Q/A check-> | 771760.4602

## 15 Other
Cobre
Stockpile Worksheet #15
Other Reclamation Activity Costs | [8 empty] | 2014-12-05
|  |  |  | Unit | Direct
|  |  |  | Cost | Cost
Item | Activity | Quantity | Unit | ($/unit) | ($) | Reference | Line Item | Page | Description
Surface Impoundments
Reinforced Concrete Wall Demolition | SWRF Dam 1 | 54 | hr | 198.0074 | 10692.4009 | Means | Crew B-12C | 541 | 1 Equip. Oper (crane), 1 laborer, 1 Hyd. Excavator, 2 C.Y. Approximately 40 hrs to demo a 200' reinforced concrete dam.
Reinforced Concrete Wall Demolition | SWRF Dam 2 | 30.6 | hr | 198.0074 | 6059.0272 | Means | Crew B-12C | 541 | 1 Equip. Oper (crane), 1 laborer, 1 Hyd. Excavator, 2 C.Y. Approximately 40 hrs to demo a 200' reinforced concrete dam.
Reinforced Concrete Wall Demolition | SWRF Dam 3 | 47 | hr | 198.0074 | 9306.349 | Means | Crew B-12C | 541 | 1 Equip. Oper (crane), 1 laborer, 1 Hyd. Excavator, 2 C.Y. Approximately 40 hrs to demo a 200' reinforced concrete dam.
Reinforced Concrete Wall Demolition | East WRF Containment | 40 | hr | 198.0074 | 7920.297 | Means | Crew B-12C | 541 | 1 Equip. Oper (crane), 1 laborer, 1 Hyd. Excavator, 2 C.Y. Approximately 40 hrs to demo a 200' reinforced concrete dam.
Wells
Plug & Abandon Well | close after 100-years | 700 | ft | 11.1302 | 7791.1146 | MMD, 2013 | $14.00/ft minus 28.3% indirect costs then added 2% inflation from 2013 to 2014. “Estimated costs for abandoning boreholes using bentonite cement grout ranges from approximately $14.00 to $25.00 per foot. For the purposes of estimating a simplified cost of abandoning boreholes the MMD cost is $14.00/ft. The FA cost estimate could be higher or lower based on site specific characteristics”.
Channels and Benches
SWRDF | Downdrain Length | 8595 | ft | 5.86 | 50366.7 | Appendix B.2.8 | Excavate and waste 7.6 cy/lf material on slopes with D11T CD, 175-foot downslope excavation, 200-foot lateral waste push. Finish grade with D6T XL SU 3 passes 1 mph.
MTI | Downdrain Length | 1353 | ft | 5.86 | 7928.58 | Appendix B.2.8 | Excavate and waste 7.6 cy/lf material on slopes with D11T CD, 175-foot downslope excavation, 200-foot lateral waste push. Finish grade with D6T XL SU 3 passes 1 mph.
SWRDF | 3:1 slope Bench Grading | 14126 | ft | 2.12 | 29947.12 | Appendix B.2.8 | Excavate and waste 9.26 cy/lf on slopes with D11T CD, 87-foot push. Finish grade with D9T SU 3 passes 1 mph.
MTI | 3:1 slope Bench Grading | 3894 | ft | 1.86 | 7242.84 | Appendix B.2.8 | Excavate and waste 9.26 cy/lf on slopes with D11T CD, 87-foot push. Finish grade with D9T SU 3 passes 1 mph.
SWRDF | 2.5:1 slope Bench Grading | 25463 | ft | 1.81 | 46088.03 | Appendix B.2.8 | Excavate and waste 9.52 cy/lf on slopes with D11T CD, 78-foot push. Finish grade with D9T SU 3 passes 1 mph.
SWRDF | Outslope Channels | 39589 | feet | 0.48 | 19002.72 | Appendix B.2.8 | Excavate and waste 0.43 cy/lf with D11T CD, 175-foot excavation, 200-foot lateral waste push. Finish grade with D6T XL SU 1 pass 1 mph.
MTI | Outslope Channels | 3894 | feet | 0.48 | 1869.12 | Appendix B.2.8 | Excavate and waste 0.43 cy/lf with D11T CD, 175-foot excavation, 200-foot lateral waste push. Finish grade with D6T XL SU 1 pass 1 mph.
SWRDF | Type 1 Top Channels | 3964 | feet | 3.28 | 13001.92 | Appendix B.2.8 | Excavate and waste 2.4 cy/lf with D11T CD, 175-foot excavation, 200-foot lateral waste push. Finish grade with D9T SU 3 passes 1 mph.
MTI | Type 2 Top Channels | 2141 | feet | 9.38 | 20082.58 | Appendix B.2.8 | Excavate and waste 2.4 cy/lf with D11T CD, 175-foot excavation, 200-foot lateral waste push. Finish grade with D9T SU 3 passes 1 mph.
Riprap & Gravel
SWRDF | Downdrain Gravel, Haul | 9025 | cy | 9.3593 | 84468.1337 | Means | G1030 150 6600 | 483 | Load & Haul rock, 3-cy loader, 7 20-cy trailers, 4-mile RT
SWRDF | Downdrain Gravel, Backfill | 9025 | cy | 0.90629 | 8179.2672 | Means | 312323.14-5200 | 238 | Gravel Backfill, 300 hp, 150' haul sand and gravel
SWRDF | Downdrain Riprap, Haul | 36959 | cy | 9.3593 | 345912.2167 | Means | G1030 150 6600 | 483 | Load & Haul rock, 3-cy loader, 7 20-cy trailers, 4-mile RT
SWRDF | Downdrain Riprap, Backfill | 36959 | cy | 0.90629 | 33495.5721 | Means | 312323.14-5200 | 238 | Gravel Backfill, 300 hp, 150' haul sand and gravel
MTI | Downdrain Gravel, Haul | 1421 | cy | 9.3593 | 13299.6364 | Means | G1030 150 6600 | 483 | Load & Haul rock, 3-cy loader, 7 20-cy trailers, 4-mile RT
MTI | Downdrain Gravel, Backfill | 1421 | cy | 0.90629 | 1287.8381 | Means | 312323.14-5200 | 238 | Gravel Backfill, 300 hp, 150' haul sand and gravel
MTI | Downdrain Riprap, Haul | 5818 | cy | 9.3593 | 54452.6983 | Means | G1030 150 6600 | 483 | Load & Haul rock, 3-cy loader, 7 20-cy trailers, 4-mile RT
MTI | Downdrain Riprap, Backfill | 5818 | cy | 0.90629 | 5272.7952 | Means | 312323.14-5200 | 238 | Gravel Backfill, 300 hp, 150' haul sand and gravel
SWRDF | Outslope Channel Riprap, Haul | 17023 | cy | 9.3593 | 159324.215 | Means | G1030 150 6600 | 483 | Load & Haul rock, 3-cy loader, 7 20-cy trailers, 4-mile RT
SWRDF | Outslope Channel Riprap, Backfill | 17023 | cy | 0.90629 | 15427.7747 | Means | 312323.14-5200 | 238 | Gravel Backfill, 300 hp, 150' haul sand and gravel
SWRDF | Top Channel Riprap, Haul | 3817 | cy | 9.3593 | 35724.639 | Means | G1030 150 6600 | 483 | Load & Haul rock, 3-cy loader, 7 20-cy trailers, 4-mile RT
SWRDF | Top Channel Riprap, Backfill | 3817 | cy | 0.90629 | 3459.3089 | Means | 312323.14-5200 | 238 | Gravel Backfill, 300 hp, 150' haul sand and gravel
MTI | Outslope Channel Riprap, Haul | 1647 | cy | 9.3593 | 15414.8494 | Means | G1030 150 6600 | 483 | Load & Haul rock, 3-cy loader, 7 20-cy trailers, 4-mile RT
MTI | Top Channel Riprap, Haul | 9206 | cy | 9.3593 | 86162.1761 | Means | G1030 150 6600 | 483 | Load & Haul rock, 3-cy loader, 7 20-cy trailers, 4-mile RT
MTI | Riprap, Backfill | 10853 | cy | 0.90629 | 9835.9654 | Means | 312323.14-5200 | 238 | Gravel Backfill, 300 hp, 150' haul sand and gravel
SWRDF | Top Channel Gravel, Haul | 2202 | cy | 9.3593 | 20609.2887 | Means | G1030 150 6600 | 483 | Load & Haul rock, 3-cy loader, 7 20-cy trailers, 4-mile RT
SWRDF | Top Channel Gravel, Backfill | 2202 | cy | 0.90629 | 1995.6506 | Means | 312323.14-5200 | 238 | Gravel Backfill, 300 hp, 150' haul sand and gravel
MTI | Top Channel Gravel, Haul | 2248 | cy | 9.3593 | 21039.8188 | Means | G1030 150 6600 | 483 | Load & Haul rock, 3-cy loader, 7 20-cy trailers, 4-mile RT
MTI | Top Channel Gravel, Backfill | 2248 | cy | 0.90629 | 2037.3399 | Means | 312323.14-5200 | 238 | Gravel Backfill, 300 hp, 150' haul sand and gravel
SWRDF | Riprap | 57799 | cy | 32.33 | 1868641.67 | Fowler Brothers Riprap Verbal Quote February 2009 $29.16/cy inflated to 2014 dollars
MTI | Riprap | 16671 | cy | 32.33 | 538973.43 | Fowler Brothers Riprap Verbal Quote February 2009 $29.16/cy inflated to 2014 dollars
SWRDF | Gravel | 11227 | cy | 4.2689 | 47926.7158 | Means | 321123.23-0301 | 302 | Base Course Drainage Layers, Crushed 1 1/2 ", Compacted to 4" deep
MTI | Gravel | 3669 | cy | 4.2689 | 15662.5207 | Means | 321123.23-0301 | 302 | Base Course Drainage Layers, Crushed 1 1/2 ", Compacted to 4" deep
Continental Pit
Safety berm, Pits perimeter |  | 6635 | feet | 2.82 | 18710.7 | Appendix B8 | Excavate 3.7 cy/lf with D6T XL SU, 100-foot push. Finish grade 1.2 cy/lf with D6T XL SU 50 ft push.
Chain link fence, Pits perimeter |  | 2453 | feet | 20.3449 | 49906.1378 | Means | 323113.20-0800 | 316 | Fence, chain link industrial, schedule 40, including concrete, 6 ga. wire, 6' high, but omit barbed wire, galv. Steel
Hanover Mountain Mine
Berm |  | 6670 | feet | 2.82 | 18809.4 | Appendix B8 | Excavate 3.7 cy/lf with D6T XL SU, 100-foot push. Finish grade 1.2 cy/lf with D6T XL SU 50 ft push.
Chain link fence |  | 3286 | feet | 20.3449 | 66853.4728 | Means | 323113.20-0800 | 316 | Fence, chain link industrial, schedule 40, including concrete, 6 ga. wire, 6' high, but omit barbed wire, galv. Steel
|  |  |  | SWRDF | 2783570.9424
|  |  |  | Hanover Mountain Deposit | 85662.8728
|  |  |  | Wells | 7791.1146
|  |  |  | MTI | 800562.1883
|  |  |  | Surface Impoundments | 33978.0741
|  |  |  | Continental Pit | 68616.8378
|  |  |  | Other Direct Cost | 3780182.0301
References
See Appendix B.2.8 for Channel, Bench, and Downdrain unit rate development.
RS Means Heavy Construction Cost Data (28st Annual Edition 2014)
| New Mexico Las Cruces | 84.7%
|  |  |  | Q/A check-> | 3780182.0301

## 16 Sum
Cobre
Stockpile Worksheet #16
Reclamation Summary |  |  |  | 2014-12-05
Cobre Mining Company
Stockpiles, Tailings, Reservoirs, Haul Roads and Distrubed Area Reclamation
Based on Projected EOY 2019 Mine Plan |  |  | Current Value
DIRECT COSTS | Facility and Structure Removal |  | -
| Earthmoving |  | 8260311.9161
| Revegetation |  | 771760.4602
| Other |  | 3780182.0301
| Subtotal, Direct Costs |  | 12812254.4064
INDIRECT COSTS1 | Mobilization and Demobilization | 3.8% | 486865.6674
| Contingencies | 4% | 512490.1763
| Engineering Redesign Fee | 2.5% | 320306.3602
| Contractor Profit and Overhead | 15% | 1921838.161
| Project Management Fee | 3% | 384367.6322
| State Procurement Cost | 0% | 0
| Indirect Percentage Sum = | 28.3%
| Subtotal, Indirect Costs |  | 3625867.997
TOTAL COST |  |  | 16438122.4034
Data Sources:
MMD. 1996. Closeout Plan Guidelines for Existing Mines, Mining Act Reclamation Bureau Mining and Minerals Division
New Mexico Energy, Minerals and Natural Resources Department. April 30, 1996.
OSM. 2000. U.S. Department of the Interior, Office of Surface Mining Reclamation and Enforcement
Handbook for Calculation of Reclamation Bond Amounts. April 5, 2000.
Notes:
1) | Indirect costs are based on the guidance available from MMD (1996) and OSM (2000).

## 17 Detailed Sum
Cobre
Stockpile Worksheet #17
Reclamation Summary | [11 empty] | 2014-12-05
DIRECT COSTS |  |  | SWRDF(a) | Hanover Mountain Deposit(b) | Pearson-Barnes Mine Area | Low Grade WRF | MTI (d) | Haul and Exploration Roads | Surface Impoundments | Wells | Continental Pit | Totals
| Earthmoving |  | 5048729.1425 | 1273697.8481 | 135852.4352 | 98783.9324 | 1628987.4549 | 14715.4129 | 59545.6901 | 0 | 0 | 8260311.9161
| Revegetation |  | 376400.9839 | 99452.7654 | 10694.2323 | 28842.0748 | 162369.0008 | 73691.3484 | 4493.3749 | 0 | 15816.6797 | 771760.4602
| Other( c) |  | 2783570.9424 | 85662.8728 | 0 | 0 | 800562.1883 | 0 | 33978.0741 | 7791.1146 | 68616.8378 | 3780182.0301
| Subtotal, Direct Costs |  | 8208701.0688 | 1458813.4863 | 146546.6675 | 127626.0073 | 2591918.644 | 88406.7613 | 98017.1391 | 7791.1146 | 84433.5175 | 12812254.4064
INDIRECT COSTS | Mobilization and Demobilization | 3.8% | 311930.6406 | 55434.9125 | 5568.7734 | 4849.7883 | 98492.9085 | 3359.4569 | 3724.6513 | 296.0624 | 3208.4737 | 486865.6674
| Contingencies | 4% | 328348.0428 | 58352.5395 | 5861.8667 | 5105.0403 | 103676.7458 | 3536.2705 | 3920.6856 | 311.6446 | 3377.3407 | 512490.1763
| Engineering Redesign Fee | 2.5% | 205217.5267 | 36470.3372 | 3663.6667 | 3190.6502 | 64797.9661 | 2210.169 | 2450.4285 | 194.7779 | 2110.8379 | 320306.3602
| Contractor Profit and Overhead | 15% | 1231305.1603 | 218822.023 | 21982.0001 | 19143.9011 | 388787.7966 | 13261.0142 | 14702.5709 | 1168.6672 | 12665.0276 | 1921838.161
| Project Management Fee | 3% | 246261.0321 | 43764.4046 | 4396.4 | 3828.7802 | 77757.5593 | 2652.2028 | 2940.5142 | 233.7334 | 2533.0055 | 384367.6322
| State Procurement Cost | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Indirect Percentage Sum = | 28.3%
| Subtotal, Indirect Costs |  | 2323062.4025 | 412844.2166 | 41472.7069 | 36118.1601 | 733512.9762 | 25019.1135 | 27738.8504 | 2204.8854 | 23894.6854 | 3625867.997
TOTAL COST PER STOCKPILE |  |  | 10531763.4713 | 1871657.703 | 188019.3744 | 163744.1673 | 3325431.6202 | 113425.8748 | 125755.9895 | 9996 | 108328.2029 | 16438122.4034
TOTAL COST |  |  | 16438122.4034
(a) Includes disturbed area adjacent and north of the SWRDF
( b) Includes berm and fence disturbed area
(c) Other includes benches, channels, downdrains, plug and abandon wells, fence, berms, and reinforced concrete wall demolition.
(d) Cost includes reclaiming south buttress area and burying tailing pipelines in place.

## 18 Facility Characteristics
Cobre
Stockpile Worksheet #18
Facility Characteristics | [8 empty] | 2014-12-05
Facility | SWRDF(a) | Hanover Mountain Deposit(b) | Pearson-Barnes Mine Area | Low Grade WRF | MTI (d) | Haul and Exploration Roads | Surface Impoundments | Wells | Continental Pit( c)
Reclaimed Acres | 418.8 | 110.7 | 11.9 | 32.1 | 180.7 | 82 | 5 | - | 17.6
Item | Capital Cost | Capital Cost | Capital Cost | Capital Cost | Capital Cost | Capital Cost | Capital Cost | Capital Cost | Capital Cost
Cover Material (Load, haul, spread) | 5415984.3324 | 1634154.3391 | 174298.6744 | 120332.14 | 1956169.2123 | 0 | 75245.9085 | 0 | 0
Regrade | 1061535.1574 | 0 | 0 | 6407.6453 | 133821.6923 | 18879.8748 | 1151.2119 | 0 | 0
Seed & Mulch | 482922.4624 | 127597.898 | 13720.7 | 37004.382 | 208319.428 | 94546 | 5765 | 0 | 20292.8
Other ( c) | 3571321.5191 | 109905.4659 | 0 | 0 | 1027121.2876 | 0 | 43593.8691 | 9996 | 88035.4029
Capital Cost Totals | 10531763.4713 | 1871657.703 | 188019.3744 | 163744.1673 | 3325431.6202 | 113425.8748 | 125755.9895 | 9996 | 108328.2029
Capital Cost/Acre | 25147.4772 | 16907.477 | 15799.9474 | 5101.0644 | 18403.0527 | 1383.2424 | 25151.1979 | - | 6155.0115
Capital Cost/Acre Cover | 12932.1498 | 14762.0085 | 14646.9474 | 3748.6648 | 10825.5075 | 0 | 15049.1817 | - | 0
Capital Cost/Acre Top/Outslope Adjustment | 2534.7067 | 0 | 0 | 199.6151 | 740.5738 | 230.2424 | 230.2424 | - | 0
Capital Cost/Acre Earthwork Total | 15466.8565 | 14762.0085 | 14646.9474 | 3948.2799 | 11566.0814 | 230.2424 | 15279.4241 | - | 0
Capital Cost/Acre Reveg | 1153.11 | 1152.6459 | 1153 | 1152.7845 | 1152.8469 | 1153 | 1153 | - | 1153
Capital Cost/Acre Other | 8527.5108 | 992.8226 | 0 | 0 | 5684.1244 | 0 | 8718.7738 | - | 5002.0115
(a) Includes disturbed area adjacent and north of the SWRDF
( b) Includes berm and fence disturbed area
(c) Other includes benches, channels, downdrains, plug and abandon wells, fence, berms, and reinforced concrete wall demolition.
(d) Cost includes reclaiming south buttress area and burying tailing pipelines in place.

## Trucks.xls
This page intentionally left blank.

## Productivity
Cobre
Stockpile Worksheet #9a
Trucks Productivity (cy/hr) | [8 empty] | 2014-12-05
Productivity (cy/hr) = | work hour (min/hr) x loader cycles per truck x net bucket capacity (cy) x no. of trucks / truck cycle time (min) | Type
Example: | 50 min/hr x 6 buckets x 11.9 cy/bucket x 8 trucks / 50 min = 571 cy/hr
No. of Trucks
Task Description | Location 1 | Location 2 | Equipment | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | 777F | 937.6352 | 1406.4528 | 1875.2705 | 2344.0881 | 2812.9057 | 3281.7233 | 3750.5409 | 4219.3585 | 4688.1761 | 5156.9937 | 5625.8114 | 6094.629 | 6563.4466 | 7032.2642 | 7501.0818 | 7969.8994 | 8438.717 | 8907.5346 | 9376.3523 | 9845.1699 | 10313.9875 | 10782.8051 | 11251.6227 | 11720.4403
Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | 777F | 937.6352 | 1406.4528 | 1875.2705 | 2344.0881 | 2812.9057 | 3281.7233 | 3750.5409 | 4219.3585 | 4688.1761 | 5156.9937 | 5625.8114 | 6094.629 | 6563.4466 | 7032.2642 | 7501.0818 | 7969.8994 | 8438.717 | 8907.5346 | 9376.3523 | 9845.1699 | 10313.9875 | 10782.8051 | 11251.6227 | 11720.4403
Haul cover soil | NOBS | SWRDF Top | 777F | 456.5235 | 684.7853 | 913.0471 | 1141.3088 | 1369.5706 | 1597.8324 | 1826.0942 | 2054.3559 | 2282.6177 | 2510.8795 | 2739.1412 | 2967.403 | 3195.6648 | 3423.9265 | 3652.1883 | 3880.4501 | 4108.7119 | 4336.9736 | 4565.2354 | 4793.4972 | 5021.7589 | 5250.0207 | 5478.2825 | 5706.5442
Haul cover soil | NOBS | Hanover Mountain Deposit | 777F | 608.5654 | 912.8481 | 1217.1309 | 1521.4136 | 1825.6963 | 2129.979 | 2434.2617 | 2738.5444 | 3042.8272 | 3347.1099 | 3651.3926 | 3955.6753 | 4259.958 | 4564.2407 | 4868.5234 | 5172.8062 | 5477.0889 | 5781.3716 | 6085.6543 | 6389.937 | 6694.2197 | 6998.5025 | 7302.7852 | 7607.0679
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | 777F | 1215.7307 | 1823.596 | 2431.4614 | 3039.3267 | 3647.1921 | 4255.0574 | 4862.9228 | 5470.7881 | 6078.6534 | 6686.5188 | 7294.3841 | 7902.2495 | 8510.1148 | 9117.9802 | 9725.8455 | 10333.7108 | 10941.5762 | 11549.4415 | 12157.3069 | 12765.1722 | 13373.0376 | 13980.9029 | 14588.7683 | 15196.6336
Haul cover soil | OB-4 Stockpile | Low Grade WRF | 777F | 1165.7257 | 1748.5886 | 2331.4514 | 2914.3143 | 3497.1771 | 4080.04 | 4662.9028 | 5245.7657 | 5828.6285 | 6411.4914 | 6994.3542 | 7577.2171 | 8160.0799 | 8742.9428 | 9325.8056 | 9908.6685 | 10491.5313 | 11074.3942 | 11657.257 | 12240.1199 | 12822.9827 | 13405.8456 | 13988.7084 | 14571.5713
Haul cover soil | NOBS | MTI Reclaim Pond | 777F | 575.8404 | 863.7606 | 1151.6807 | 1439.6009 | 1727.5211 | 2015.4413 | 2303.3615 | 2591.2817 | 2879.2018 | 3167.122 | 3455.0422 | 3742.9624 | 4030.8826 | 4318.8028 | 4606.7229 | 4894.6431 | 5182.5633 | 5470.4835 | 5758.4037 | 6046.3239 | 6334.244 | 6622.1642 | 6910.0844 | 7198.0046
Haul cover soil | NOBS | MTI Top | 777F | 575.8404 | 863.7606 | 1151.6807 | 1439.6009 | 1727.5211 | 2015.4413 | 2303.3615 | 2591.2817 | 2879.2018 | 3167.122 | 3455.0422 | 3742.9624 | 4030.8826 | 4318.8028 | 4606.7229 | 4894.6431 | 5182.5633 | 5470.4835 | 5758.4037 | 6046.3239 | 6334.244 | 6622.1642 | 6910.0844 | 7198.0046
Haul cover soil | NOBS | MTI Outslope | 777F | 575.8404 | 863.7606 | 1151.6807 | 1439.6009 | 1727.5211 | 2015.4413 | 2303.3615 | 2591.2817 | 2879.2018 | 3167.122 | 3455.0422 | 3742.9624 | 4030.8826 | 4318.8028 | 4606.7229 | 4894.6431 | 5182.5633 | 5470.4835 | 5758.4037 | 6046.3239 | 6334.244 | 6622.1642 | 6910.0844 | 7198.0046
Haul cover soil | Reclaim Pond Outlet Channel | MTI Top | 777F | 1178.4899 | 1767.7349 | 2356.9798 | 2946.2248 | 3535.4697 | 4124.7147 | 4713.9596 | 5303.2046 | 5892.4495 | 6481.6945 | 7070.9394 | 7660.1844 | 8249.4293 | 8838.6743 | 9427.9192 | 10017.1642 | 10606.4091 | 11195.6541 | 11784.899 | 12374.144 | 12963.3889 | 13552.6339 | 14141.8788 | 14731.1238
Haul cover soil | NOBS | Tailing Pipeline Corridor | 777F | 575.8404 | 863.7606 | 1151.6807 | 1439.6009 | 1727.5211 | 2015.4413 | 2303.3615 | 2591.2817 | 2879.2018 | 3167.122 | 3455.0422 | 3742.9624 | 4030.8826 | 4318.8028 | 4606.7229 | 4894.6431 | 5182.5633 | 5470.4835 | 5758.4037 | 6046.3239 | 6334.244 | 6622.1642 | 6910.0844 | 7198.0046
Haul cover soil | NOBS | Grape Gulch Pond #3 | 777F | 804.381 | 1206.5715 | 1608.7619 | 2010.9524 | 2413.1429 | 2815.3334 | 3217.5239 | 3619.7144 | 4021.9049 | 4424.0953 | 4826.2858 | 5228.4763 | 5630.6668 | 6032.8573 | 6435.0478 | 6837.2382 | 7239.4287 | 7641.6192 | 8043.8097 | 8446.0002 | 8848.1907 | 9250.3812 | 9652.5716 | 10054.7621
Haul cover soil | NOBS | Magnetite Seepage Pond | 777F | 672.0536 | 1008.0804 | 1344.1072 | 1680.1341 | 2016.1609 | 2352.1877 | 2688.2145 | 3024.2413 | 3360.2681 | 3696.2949 | 4032.3217 | 4368.3485 | 4704.3753 | 5040.4022 | 5376.429 | 5712.4558 | 6048.4826 | 6384.5094 | 6720.5362 | 7056.563 | 7392.5898 | 7728.6166 | 8064.6434 | 8400.6703
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | 777F | 937.6352 | 1406.4528 | 1875.2705 | 2344.0881 | 2812.9057 | 3281.7233 | 3750.5409 | 4219.3585 | 4688.1761 | 5156.9937 | 5625.8114 | 6094.629 | 6563.4466 | 7032.2642 | 7501.0818 | 7969.8994 | 8438.717 | 8907.5346 | 9376.3523 | 9845.1699 | 10313.9875 | 10782.8051 | 11251.6227 | 11720.4403
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | 777F | 937.6352 | 1406.4528 | 1875.2705 | 2344.0881 | 2812.9057 | 3281.7233 | 3750.5409 | 4219.3585 | 4688.1761 | 5156.9937 | 5625.8114 | 6094.629 | 6563.4466 | 7032.2642 | 7501.0818 | 7969.8994 | 8438.717 | 8907.5346 | 9376.3523 | 9845.1699 | 10313.9875 | 10782.8051 | 11251.6227 | 11720.4403
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | 777F | 937.6352 | 1406.4528 | 1875.2705 | 2344.0881 | 2812.9057 | 3281.7233 | 3750.5409 | 4219.3585 | 4688.1761 | 5156.9937 | 5625.8114 | 6094.629 | 6563.4466 | 7032.2642 | 7501.0818 | 7969.8994 | 8438.717 | 8907.5346 | 9376.3523 | 9845.1699 | 10313.9875 | 10782.8051 | 11251.6227 | 11720.4403
Haul cover soil | OB-4 Stockpile | North Tailings Decant Pond | 777F | 1165.7257 | 1748.5886 | 2331.4514 | 2914.3143 | 3497.1771 | 4080.04 | 4662.9028 | 5245.7657 | 5828.6285 | 6411.4914 | 6994.3542 | 7577.2171 | 8160.0799 | 8742.9428 | 9325.8056 | 9908.6685 | 10491.5313 | 11074.3942 | 11657.257 | 12240.1199 | 12822.9827 | 13405.8456 | 13988.7084 | 14571.5713
Haul cover soil | OB-4 Stockpile | East WRF Containment | 777F | 1165.7257 | 1748.5886 | 2331.4514 | 2914.3143 | 3497.1771 | 4080.04 | 4662.9028 | 5245.7657 | 5828.6285 | 6411.4914 | 6994.3542 | 7577.2171 | 8160.0799 | 8742.9428 | 9325.8056 | 9908.6685 | 10491.5313 | 11074.3942 | 11657.257 | 12240.1199 | 12822.9827 | 13405.8456 | 13988.7084 | 14571.5713
Haul cover soil | NOBS | Blackman's Seep (Pond #2) | 777F | 804.381 | 1206.5715 | 1608.7619 | 2010.9524 | 2413.1429 | 2815.3334 | 3217.5239 | 3619.7144 | 4021.9049 | 4424.0953 | 4826.2858 | 5228.4763 | 5630.6668 | 6032.8573 | 6435.0478 | 6837.2382 | 7239.4287 | 7641.6192 | 8043.8097 | 8446.0002 | 8848.1907 | 9250.3812 | 9652.5716 | 10054.7621
Haul cover soil | OB-4 Stockpile | Decant Pond #4 | 777F | 1165.7257 | 1748.5886 | 2331.4514 | 2914.3143 | 3497.1771 | 4080.04 | 4662.9028 | 5245.7657 | 5828.6285 | 6411.4914 | 6994.3542 | 7577.2171 | 8160.0799 | 8742.9428 | 9325.8056 | 9908.6685 | 10491.5313 | 11074.3942 | 11657.257 | 12240.1199 | 12822.9827 | 13405.8456 | 13988.7084 | 14571.5713
Haul cover soil | NOBS | Upper Creek Containment Pond 1 | 777F | 804.381 | 1206.5715 | 1608.7619 | 2010.9524 | 2413.1429 | 2815.3334 | 3217.5239 | 3619.7144 | 4021.9049 | 4424.0953 | 4826.2858 | 5228.4763 | 5630.6668 | 6032.8573 | 6435.0478 | 6837.2382 | 7239.4287 | 7641.6192 | 8043.8097 | 8446.0002 | 8848.1907 | 9250.3812 | 9652.5716 | 10054.7621

## Time
Cobre
Stockpile Worksheet #9b
Truck Time (hours) | [14 empty] | 2014-12-05
Truck Time (hr) = | If vol./prod. (cy/cy per hr)<loader task time (hr), then use loader task time (hr); if not, use vol./ prod. (cy/cy per hr)
Example: | 1,000,000 cy / 571 cy/hr = 1,751 hr < 2,000 hr =====> 2,000 hr
No. of Trucks
Task Description | Location 1 | Location 2 | Equipment | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | 777F | 439.7958 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131 | 382.9131
Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | 777F | 1319.3873 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394 | 1148.7394
Haul cover soil | NOBS | SWRDF Top | 777F | 261.866 | 174.5773 | 130.933 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089 | 111.0089
Haul cover soil | NOBS | Hanover Mountain Deposit | 777F | 742.027 | 494.6847 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169 | 419.3169
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | 777F | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482 | 53.482
Haul cover soil | OB-4 Stockpile | Low Grade WRF | 777F | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692 | 41.692
Haul cover soil | NOBS | MTI Reclaim Pond | 777F | 277.3685 | 184.9124 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114 | 148.3114
Haul cover soil | NOBS | MTI Top | 777F | 330.4459 | 220.2973 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924 | 176.6924
Haul cover soil | NOBS | MTI Outslope | 777F | 305.3575 | 203.5717 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774 | 163.2774
Haul cover soil | Reclaim Pond Outlet Channel | MTI Top | 777F | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485 | 66.4485
Haul cover soil | NOBS | Tailing Pipeline Corridor | 777F | 12.1538 | 8.1025 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987 | 6.4987
Haul cover soil | NOBS | Grape Gulch Pond #3 | 777F | 2.2865 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078 | 1.7078
Haul cover soil | NOBS | Magnetite Seepage Pond | 777F | 1.4404 | 0.96024 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886 | 0.89886
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | 777F | 2.6842 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337 | 2.337
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | 777F | 1.7551 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281 | 1.5281
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | 777F | 4.336 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752 | 3.7752
Haul cover soil | OB-4 Stockpile | North Tailings Decant Pond | 777F | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674 | 2.0674
Haul cover soil | OB-4 Stockpile | East WRF Containment | 777F | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471 | 2.2471
Haul cover soil | NOBS | Blackman's Seep (Pond #2) | 777F | 0.06017 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943 | 0.044943
Haul cover soil | OB-4 Stockpile | Decant Pond #4 | 777F | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865 | 2.7865
Haul cover soil | NOBS | Upper Creek Containment Pond 1 | 777F | 6.7993 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785 | 5.0785

## TruckCost
Cobre
Stockpile Worksheet #9c
Truck Cost | [10 empty] | 2014-12-05
Truck Cost ($) = | Truck time (hr) x [owning/operating cost ($/hr) + labor cost ($/hr)] x no. of trucks
Example: | 5,000 hr x ($187.01/hr + $20.00/hr) x 8 trucks = $8,280,400
No. of Trucks
Task Description | Location 1 | Location 2 | Equipment | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | 777F | 296615.8549 | 387377.9101 | 516503.8801 | 645629.8502 | 774755.8202 | 903881.7902 | 1033007.7603 | 1162133.7303 | 1291259.7003 | 1420385.6704 | 1549511.6404 | 1678637.6104 | 1807763.5805 | 1936889.5505 | 2066015.5205 | 2195141.4906 | 2324267.4606 | 2453393.4307 | 2582519.4007 | 2711645.3707 | 2840771.3408 | 2969897.3108 | 3099023.2808 | 3228149.2509
Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | 777F | 889847.5646 | 1162133.7303 | 1549511.6404 | 1936889.5505 | 2324267.4606 | 2711645.3707 | 3099023.2808 | 3486401.1909 | 3873779.101 | 4261157.0111 | 4648534.9212 | 5035912.8313 | 5423290.7414 | 5810668.6515 | 6198046.5616 | 6585424.4717 | 6972802.3819 | 7360180.292 | 7747558.2021 | 8134936.1122 | 8522314.0223 | 8909691.9324 | 9297069.8425 | 9684447.7526
Haul cover soil | NOBS | SWRDF Top | 777F | 176612.915 | 176612.915 | 176612.915 | 187172.034 | 224606.4408 | 262040.8476 | 299475.2544 | 336909.6613 | 374344.0681 | 411778.4749 | 449212.8817 | 486647.2885 | 524081.6953 | 561516.1021 | 598950.5089 | 636384.9157 | 673819.3225 | 711253.7293 | 748688.1361 | 786122.5429 | 823556.9497 | 860991.3565 | 898425.7633 | 935860.1701
Haul cover soil | NOBS | Hanover Mountain Deposit | 777F | 500452.7111 | 500452.7111 | 565608.1223 | 707010.1528 | 848412.1834 | 989814.214 | 1131216.2445 | 1272618.2751 | 1414020.3057 | 1555422.3362 | 1696824.3668 | 1838226.3974 | 1979628.4279 | 2121030.4585 | 2262432.4891 | 2403834.5196 | 2545236.5502 | 2686638.5807 | 2828040.6113 | 2969442.6419 | 3110844.6724 | 3252246.703 | 3393648.7336 | 3535050.7641
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | 777F | 36070.4001 | 54105.6001 | 72140.8002 | 90176.0002 | 108211.2002 | 126246.4003 | 144281.6003 | 162316.8004 | 180352.0004 | 198387.2004 | 216422.4005 | 234457.6005 | 252492.8006 | 270528.0006 | 288563.2006 | 306598.4007 | 324633.6007 | 342668.8008 | 360704.0008 | 378739.2008 | 396774.4009 | 414809.6009 | 432844.801 | 450880.001
Haul cover soil | OB-4 Stockpile | Low Grade WRF | 777F | 28118.7461 | 42178.1191 | 56237.4921 | 70296.8651 | 84356.2382 | 98415.6112 | 112474.9842 | 126534.3573 | 140593.7303 | 154653.1033 | 168712.4763 | 182771.8494 | 196831.2224 | 210890.5954 | 224949.9685 | 239009.3415 | 253068.7145 | 267128.0875 | 281187.4606 | 295246.8336 | 309306.2066 | 323365.5797 | 337424.9527 | 351484.3257
Haul cover soil | NOBS | MTI Reclaim Pond | 777F | 187068.4359 | 187068.4359 | 200054.3198 | 250067.8997 | 300081.4797 | 350095.0596 | 400108.6395 | 450122.2195 | 500135.7994 | 550149.3794 | 600162.9593 | 650176.5393 | 700190.1192 | 750203.6991 | 800217.2791 | 850230.859 | 900244.439 | 950258.0189 | 1000271.5989 | 1050285.1788 | 1100298.7587 | 1150312.3387 | 1200325.9186 | 1250339.4986
Haul cover soil | NOBS | MTI Top | 777F | 222865.9465 | 222865.9465 | 238336.8156 | 297921.0195 | 357505.2234 | 417089.4273 | 476673.6312 | 536257.8351 | 595842.039 | 655426.2429 | 715010.4468 | 774594.6507 | 834178.8546 | 893763.0585 | 953347.2624 | 1012931.4663 | 1072515.6702 | 1132099.8741 | 1191684.078 | 1251268.2819 | 1310852.4858 | 1370436.6897 | 1430020.8936 | 1489605.0975
Haul cover soil | NOBS | MTI Outslope | 777F | 205945.3417 | 205945.3417 | 220241.6193 | 275302.0241 | 330362.429 | 385422.8338 | 440483.2386 | 495543.6435 | 550604.0483 | 605664.4531 | 660724.8579 | 715785.2628 | 770845.6676 | 825906.0724 | 880966.4772 | 936026.8821 | 991087.2869 | 1046147.6917 | 1101208.0966 | 1156268.5014 | 1211328.9062 | 1266389.311 | 1321449.7159 | 1376510.1207
Haul cover soil | Reclaim Pond Outlet Channel | MTI Top | 777F | 44815.5119 | 67223.2678 | 89631.0238 | 112038.7797 | 134446.5357 | 156854.2916 | 179262.0476 | 201669.8035 | 224077.5594 | 246485.3154 | 268893.0713 | 291300.8273 | 313708.5832 | 336116.3392 | 358524.0951 | 380931.851 | 403339.607 | 425747.3629 | 448155.1189 | 470562.8748 | 492970.6308 | 515378.3867 | 537786.1427 | 560193.8986
Haul cover soil | NOBS | Tailing Pipeline Corridor | 777F | 8196.9987 | 8196.9987 | 8766.0166 | 10957.5207 | 13149.0248 | 15340.529 | 17532.0331 | 19723.5373 | 21915.0414 | 24106.5455 | 26298.0497 | 28489.5538 | 30681.058 | 32872.5621 | 35064.0662 | 37255.5704 | 39447.0745 | 41638.5786 | 43830.0828 | 46021.5869 | 48213.0911 | 50404.5952 | 52596.0993 | 54787.6035
Haul cover soil | NOBS | Grape Gulch Pond #3 | 777F | 1542.0927 | 1727.7419 | 2303.6558 | 2879.5698 | 3455.4837 | 4031.3977 | 4607.3116 | 5183.2256 | 5759.1395 | 6335.0535 | 6910.9674 | 7486.8814 | 8062.7953 | 8638.7093 | 9214.6232 | 9790.5372 | 10366.4511 | 10942.3651 | 11518.279 | 12094.193 | 12670.1069 | 13246.0209 | 13821.9348 | 14397.8488
Haul cover soil | NOBS | Magnetite Seepage Pond | 777F | 971.4372 | 971.4372 | 1212.4504 | 1515.563 | 1818.6756 | 2121.7882 | 2424.9008 | 2728.0135 | 3031.1261 | 3334.2387 | 3637.3513 | 3940.4639 | 4243.5765 | 4546.6891 | 4849.8017 | 5152.9143 | 5456.0269 | 5759.1395 | 6062.2521 | 6365.3647 | 6668.4773 | 6971.5899 | 7274.7025 | 7577.8151
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | 777F | 1810.3315 | 2364.2783 | 3152.3711 | 3940.4639 | 4728.5566 | 5516.6494 | 6304.7422 | 7092.835 | 7880.9277 | 8669.0205 | 9457.1133 | 10245.2061 | 11033.2988 | 11821.3916 | 12609.4844 | 13397.5772 | 14185.6699 | 14973.7627 | 15761.8555 | 16549.9483 | 17338.041 | 18126.1338 | 18914.2266 | 19702.3194
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | 777F | 1183.6783 | 1545.8743 | 2061.1657 | 2576.4571 | 3091.7486 | 3607.04 | 4122.3314 | 4637.6229 | 5152.9143 | 5668.2057 | 6183.4972 | 6698.7886 | 7214.08 | 7729.3714 | 8244.6629 | 8759.9543 | 9275.2457 | 9790.5372 | 10305.8286 | 10821.12 | 11336.4115 | 11851.7029 | 12366.9943 | 12882.2857
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | 777F | 2924.3817 | 3819.2188 | 5092.2918 | 6365.3647 | 7638.4377 | 8911.5106 | 10184.5836 | 11457.6565 | 12730.7294 | 14003.8024 | 15276.8753 | 16549.9483 | 17823.0212 | 19096.0942 | 20369.1671 | 21642.24 | 22915.313 | 24188.3859 | 25461.4589 | 26734.5318 | 28007.6048 | 29280.6777 | 30553.7507 | 31826.8236
Haul cover soil | OB-4 Stockpile | North Tailings Decant Pond | 777F | 1394.318 | 2091.477 | 2788.636 | 3485.795 | 4182.954 | 4880.113 | 5577.2719 | 6274.4309 | 6971.5899 | 7668.7489 | 8365.9079 | 9063.0669 | 9760.2259 | 10457.3849 | 11154.5439 | 11851.7029 | 12548.8619 | 13246.0209 | 13943.1799 | 14640.3389 | 15337.4978 | 16034.6568 | 16731.8158 | 17428.9748
Haul cover soil | OB-4 Stockpile | East WRF Containment | 777F | 1515.563 | 2273.3445 | 3031.1261 | 3788.9076 | 4546.6891 | 5304.4706 | 6062.2521 | 6820.0336 | 7577.8151 | 8335.5967 | 9093.3782 | 9851.1597 | 10608.9412 | 11366.7227 | 12124.5042 | 12882.2857 | 13640.0673 | 14397.8488 | 15155.6303 | 15913.4118 | 16671.1933 | 17428.9748 | 18186.7563 | 18944.5379
Haul cover soil | NOBS | Blackman's Seep (Pond #2) | 777F | 40.5814 | 45.4669 | 60.6225 | 75.7782 | 90.9338 | 106.0894 | 121.245 | 136.4007 | 151.5563 | 166.7119 | 181.8676 | 197.0232 | 212.1788 | 227.3345 | 242.4901 | 257.6457 | 272.8013 | 287.957 | 303.1126 | 318.2682 | 333.4239 | 348.5795 | 363.7351 | 378.8908
Haul cover soil | OB-4 Stockpile | Decant Pond #4 | 777F | 1879.2982 | 2818.9472 | 3758.5963 | 4698.2454 | 5637.8945 | 6577.5435 | 7517.1926 | 8456.8417 | 9396.4908 | 10336.1399 | 11275.7889 | 12215.438 | 13155.0871 | 14094.7362 | 15034.3852 | 15974.0343 | 16913.6834 | 17853.3325 | 18792.9816 | 19732.6306 | 20672.2797 | 21611.9288 | 22551.5779 | 23491.2269
Haul cover soil | NOBS | Upper Creek Containment Pond 1 | 777F | 4585.6968 | 5137.7587 | 6850.3449 | 8562.9311 | 10275.5173 | 11988.1036 | 13700.6898 | 15413.276 | 17125.8622 | 18838.4484 | 20551.0347 | 22263.6209 | 23976.2071 | 25688.7933 | 27401.3796 | 29113.9658 | 30826.552 | 32539.1382 | 34251.7244 | 35964.3107 | 37676.8969 | 39389.4831 | 41102.0693 | 42814.6556

## LoaderCost
Cobre
Stockpile Worksheet #9d
Loader Cost | [10 empty] | 2014-12-05
Loader Cost ($) = | Loader time (hr) x [owning/operating cost ($/hr) + labor cost ($/hr)]
Example: | 5,000 hr x ($206.13/hr + $20.00/hr) = $1,130,650
|  |  | Equipment | No. of Trucks
Task Description | Location 1 | Location 2 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | 992K | 183711.4864 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478 | 159950.478
Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | 992K | 551134.4592 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341 | 479851.4341
Haul cover soil | NOBS | SWRDF Top | 992K | 109386.6717 | 72924.4478 | 54693.3359 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198 | 46370.6198
Haul cover soil | NOBS | Hanover Mountain Deposit | 992K | 309959.5316 | 206639.6877 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376 | 175157.0376
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | 992K | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501 | 22340.501
Haul cover soil | OB-4 Stockpile | Low Grade WRF | 992K | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783 | 17415.5783
Haul cover soil | NOBS | MTI Reclaim Pond | 992K | 115862.3852 | 77241.5901 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499 | 61952.6499
Haul cover soil | NOBS | MTI Top | 992K | 138033.8698 | 92022.5799 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404 | 73807.9404
Haul cover soil | NOBS | MTI Outslope | 992K | 127553.9531 | 85035.9688 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355 | 68204.2355
Haul cover soil | Reclaim Pond Outlet Channel | MTI Top | 992K | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585 | 27756.8585
Haul cover soil | NOBS | Tailing Pipeline Corridor | 992K | 5076.8791 | 3384.586 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525 | 2714.6525
Haul cover soil | NOBS | Grape Gulch Pond #3 | 992K | 955.1079 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942 | 713.3942
Haul cover soil | NOBS | Magnetite Seepage Pond | 992K | 601.6677 | 401.1118 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706 | 375.4706
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | 992K | 1121.2438 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236 | 976.2236
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | 992K | 733.121 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3 | 638.3
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | 992K | 1811.24 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765 | 1576.9765
Haul cover soil | OB-4 Stockpile | North Tailings Decant Pond | 992K | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824 | 863.5824
Haul cover soil | OB-4 Stockpile | East WRF Containment | 992K | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765 | 938.6765
Haul cover soil | NOBS | Blackman's Seep (Pond #2) | 992K | 25.1344 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735 | 18.7735
Haul cover soil | OB-4 Stockpile | Decant Pond #4 | 992K | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589 | 1163.9589
Haul cover soil | NOBS | Upper Creek Containment Pond 1 | 992K | 2840.1893 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089 | 2121.4089

## TotalCost
Cobre
Stockpile Worksheet #9e
Trucks & Loader Total Cost | [10 empty] | 2014-12-05
Total Cost ($) = | Truck Cost ($) + Loader Cost ($)
Example: | $8,280,400 + $1,130,650 = $9,411,050
|  |  |  | No. of Trucks | [23 empty] | Minimum
Task Description | Location 1 | Location 2 | Equipment | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | Cost
Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | 777F | 480327.3413 | 547328.3881 | 676454.3582 | 805580.3282 | 934706.2982 | 1063832.2683 | 1192958.2383 | 1322084.2083 | 1451210.1784 | 1580336.1484 | 1709462.1184 | 1838588.0885 | 1967714.0585 | 2096840.0285 | 2225965.9986 | 2355091.9686 | 2484217.9387 | 2613343.9087 | 2742469.8787 | 2871595.8488 | 3000721.8188 | 3129847.7888 | 3258973.7589 | 3388099.7289 | 480327.3413
Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | 777F | 1440982.0239 | 1641985.1644 | 2029363.0745 | 2416740.9846 | 2804118.8947 | 3191496.8048 | 3578874.7149 | 3966252.625 | 4353630.5351 | 4741008.4452 | 5128386.3553 | 5515764.2654 | 5903142.1755 | 6290520.0856 | 6677897.9957 | 7065275.9059 | 7452653.816 | 7840031.7261 | 8227409.6362 | 8614787.5463 | 9002165.4564 | 9389543.3665 | 9776921.2766 | 10164299.1867 | 1440982.0239
Haul cover soil | NOBS | SWRDF Top | 777F | 285999.5867 | 249537.3628 | 231306.2509 | 233542.6538 | 270977.0606 | 308411.4674 | 345845.8743 | 383280.2811 | 420714.6879 | 458149.0947 | 495583.5015 | 533017.9083 | 570452.3151 | 607886.7219 | 645321.1287 | 682755.5355 | 720189.9423 | 757624.3491 | 795058.7559 | 832493.1627 | 869927.5695 | 907361.9763 | 944796.3831 | 982230.7899 | 231306.2509
Haul cover soil | NOBS | Hanover Mountain Deposit | 777F | 810412.2426 | 707092.3988 | 740765.1598 | 882167.1904 | 1023569.221 | 1164971.2515 | 1306373.2821 | 1447775.3127 | 1589177.3432 | 1730579.3738 | 1871981.4044 | 2013383.4349 | 2154785.4655 | 2296187.4961 | 2437589.5266 | 2578991.5572 | 2720393.5877 | 2861795.6183 | 3003197.6489 | 3144599.6794 | 3286001.71 | 3427403.7406 | 3568805.7711 | 3710207.8017 | 707092.3988
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | 777F | 58410.9011 | 76446.1012 | 94481.3012 | 112516.5012 | 130551.7013 | 148586.9013 | 166622.1014 | 184657.3014 | 202692.5014 | 220727.7015 | 238762.9015 | 256798.1016 | 274833.3016 | 292868.5016 | 310903.7017 | 328938.9017 | 346974.1018 | 365009.3018 | 383044.5018 | 401079.7019 | 419114.9019 | 437150.102 | 455185.302 | 473220.502 | 58410.9011
Haul cover soil | OB-4 Stockpile | Low Grade WRF | 777F | 45534.3243 | 59593.6973 | 73653.0704 | 87712.4434 | 101771.8164 | 115831.1895 | 129890.5625 | 143949.9355 | 158009.3085 | 172068.6816 | 186128.0546 | 200187.4276 | 214246.8007 | 228306.1737 | 242365.5467 | 256424.9197 | 270484.2928 | 284543.6658 | 298603.0388 | 312662.4119 | 326721.7849 | 340781.1579 | 354840.5309 | 368899.904 | 45534.3243
Haul cover soil | NOBS | MTI Reclaim Pond | 777F | 302930.8211 | 264310.0261 | 262006.9697 | 312020.5497 | 362034.1296 | 412047.7095 | 462061.2895 | 512074.8694 | 562088.4494 | 612102.0293 | 662115.6093 | 712129.1892 | 762142.7691 | 812156.3491 | 862169.929 | 912183.509 | 962197.0889 | 1012210.6689 | 1062224.2488 | 1112237.8287 | 1162251.4087 | 1212264.9886 | 1262278.5686 | 1312292.1485 | 262006.9697
Haul cover soil | NOBS | MTI Top | 777F | 360899.8163 | 314888.5264 | 312144.756 | 371728.9599 | 431313.1638 | 490897.3677 | 550481.5716 | 610065.7755 | 669649.9794 | 729234.1833 | 788818.3872 | 848402.5911 | 907986.795 | 967570.9989 | 1027155.2028 | 1086739.4067 | 1146323.6106 | 1205907.8145 | 1265492.0184 | 1325076.2223 | 1384660.4262 | 1444244.6301 | 1503828.834 | 1563413.0379 | 312144.756
Haul cover soil | NOBS | MTI Outslope | 777F | 333499.2949 | 290981.3105 | 288445.8548 | 343506.2597 | 398566.6645 | 453627.0693 | 508687.4742 | 563747.879 | 618808.2838 | 673868.6886 | 728929.0935 | 783989.4983 | 839049.9031 | 894110.3079 | 949170.7128 | 1004231.1176 | 1059291.5224 | 1114351.9273 | 1169412.3321 | 1224472.7369 | 1279533.1417 | 1334593.5466 | 1389653.9514 | 1444714.3562 | 288445.8548
Haul cover soil | Reclaim Pond Outlet Channel | MTI Top | 777F | 72572.3704 | 94980.1263 | 117387.8822 | 139795.6382 | 162203.3941 | 184611.1501 | 207018.906 | 229426.662 | 251834.4179 | 274242.1739 | 296649.9298 | 319057.6857 | 341465.4417 | 363873.1976 | 386280.9536 | 408688.7095 | 431096.4655 | 453504.2214 | 475911.9773 | 498319.7333 | 520727.4892 | 543135.2452 | 565543.0011 | 587950.7571 | 72572.3704
Haul cover soil | NOBS | Tailing Pipeline Corridor | 777F | 13273.8778 | 11581.5848 | 11480.669 | 13672.1732 | 15863.6773 | 18055.1815 | 20246.6856 | 22438.1897 | 24629.6939 | 26821.198 | 29012.7022 | 31204.2063 | 33395.7104 | 35587.2146 | 37778.7187 | 39970.2228 | 42161.727 | 44353.2311 | 46544.7353 | 48736.2394 | 50927.7435 | 53119.2477 | 55310.7518 | 57502.256 | 11480.669
Haul cover soil | NOBS | Grape Gulch Pond #3 | 777F | 2497.2006 | 2441.136 | 3017.05 | 3592.9639 | 4168.8779 | 4744.7918 | 5320.7058 | 5896.6197 | 6472.5337 | 7048.4476 | 7624.3616 | 8200.2755 | 8776.1895 | 9352.1034 | 9928.0174 | 10503.9313 | 11079.8453 | 11655.7592 | 12231.6732 | 12807.5871 | 13383.5011 | 13959.415 | 14535.329 | 15111.2429 | 2441.136
Haul cover soil | NOBS | Magnetite Seepage Pond | 777F | 1573.105 | 1372.5491 | 1587.921 | 1891.0336 | 2194.1462 | 2497.2588 | 2800.3715 | 3103.4841 | 3406.5967 | 3709.7093 | 4012.8219 | 4315.9345 | 4619.0471 | 4922.1597 | 5225.2723 | 5528.3849 | 5831.4975 | 6134.6101 | 6437.7227 | 6740.8353 | 7043.9479 | 7347.0605 | 7650.1731 | 7953.2857 | 1372.5491
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | 777F | 2931.5753 | 3340.5019 | 4128.5947 | 4916.6874 | 5704.7802 | 6492.873 | 7280.9658 | 8069.0585 | 8857.1513 | 9645.2441 | 10433.3369 | 11221.4296 | 12009.5224 | 12797.6152 | 13585.708 | 14373.8007 | 15161.8935 | 15949.9863 | 16738.0791 | 17526.1718 | 18314.2646 | 19102.3574 | 19890.4502 | 20678.5429 | 2931.5753
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | 777F | 1916.7992 | 2184.1743 | 2699.4657 | 3214.7572 | 3730.0486 | 4245.34 | 4760.6315 | 5275.9229 | 5791.2143 | 6306.5058 | 6821.7972 | 7337.0886 | 7852.38 | 8367.6715 | 8882.9629 | 9398.2543 | 9913.5458 | 10428.8372 | 10944.1286 | 11459.4201 | 11974.7115 | 12490.0029 | 13005.2943 | 13520.5858 | 1916.7992
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | 777F | 4735.6217 | 5396.1954 | 6669.2683 | 7942.3413 | 9215.4142 | 10488.4872 | 11761.5601 | 13034.633 | 14307.706 | 15580.7789 | 16853.8519 | 18126.9248 | 19399.9978 | 20673.0707 | 21946.1436 | 23219.2166 | 24492.2895 | 25765.3625 | 27038.4354 | 28311.5084 | 29584.5813 | 30857.6543 | 32130.7272 | 33403.8001 | 4735.6217
Haul cover soil | OB-4 Stockpile | North Tailings Decant Pond | 777F | 2257.9004 | 2955.0594 | 3652.2184 | 4349.3774 | 5046.5364 | 5743.6953 | 6440.8543 | 7138.0133 | 7835.1723 | 8532.3313 | 9229.4903 | 9926.6493 | 10623.8083 | 11320.9673 | 12018.1263 | 12715.2853 | 13412.4443 | 14109.6033 | 14806.7623 | 15503.9212 | 16201.0802 | 16898.2392 | 17595.3982 | 18292.5572 | 2257.9004
Haul cover soil | OB-4 Stockpile | East WRF Containment | 777F | 2454.2395 | 3212.0211 | 3969.8026 | 4727.5841 | 5485.3656 | 6243.1471 | 7000.9286 | 7758.7101 | 8516.4917 | 9274.2732 | 10032.0547 | 10789.8362 | 11547.6177 | 12305.3992 | 13063.1807 | 13820.9623 | 14578.7438 | 15336.5253 | 16094.3068 | 16852.0883 | 17609.8698 | 18367.6513 | 19125.4329 | 19883.2144 | 2454.2395
Haul cover soil | NOBS | Blackman's Seep (Pond #2) | 777F | 65.7158 | 64.2404 | 79.3961 | 94.5517 | 109.7073 | 124.8629 | 140.0186 | 155.1742 | 170.3298 | 185.4855 | 200.6411 | 215.7967 | 230.9524 | 246.108 | 261.2636 | 276.4192 | 291.5749 | 306.7305 | 321.8861 | 337.0418 | 352.1974 | 367.353 | 382.5087 | 397.6643 | 64.2404
Haul cover soil | OB-4 Stockpile | Decant Pond #4 | 777F | 3043.257 | 3982.9061 | 4922.5552 | 5862.2043 | 6801.8533 | 7741.5024 | 8681.1515 | 9620.8006 | 10560.4497 | 11500.0987 | 12439.7478 | 13379.3969 | 14319.046 | 15258.695 | 16198.3441 | 17137.9932 | 18077.6423 | 19017.2914 | 19956.9404 | 20896.5895 | 21836.2386 | 22775.8877 | 23715.5367 | 24655.1858 | 3043.257
Haul cover soil | NOBS | Upper Creek Containment Pond 1 | 777F | 7425.8861 | 7259.1676 | 8971.7538 | 10684.34 | 12396.9263 | 14109.5125 | 15822.0987 | 17534.6849 | 19247.2711 | 20959.8574 | 22672.4436 | 24385.0298 | 26097.616 | 27810.2023 | 29522.7885 | 31235.3747 | 32947.9609 | 34660.5471 | 36373.1334 | 38085.7196 | 39798.3058 | 41510.892 | 43223.4783 | 44936.0645 | 7259.1676

## Optimum
Cobre
Stockpile Worksheet #9f
Trucks Optimum | [27 empty] | 2014-12-05
Optimum = | If minimum total cost >or = total cost for this no. of trucks, then enter this no. of trucks; if not, enter zero
Example: | $4,478,191 < $6,060,707 =====> enter zero
Optimum
|  |  |  | No. of Trucks | [23 empty] | No. of
Task Description | Location 1 | Location 2 | Equipment | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | Trucks
16438122.4034
Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Top | 777F | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Haul cover soil | OB Stockpile 1 through 4, Topsoil Stockpile, South OB Stockpile | SWRDF Outslopes | 777F | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Haul cover soil | NOBS | SWRDF Top | 777F | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Haul cover soil | NOBS | Hanover Mountain Deposit | 777F | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | Pearson-Barnes Mine Area | 777F | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Haul cover soil | OB-4 Stockpile | Low Grade WRF | 777F | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Haul cover soil | NOBS | MTI Reclaim Pond | 777F | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Haul cover soil | NOBS | MTI Top | 777F | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Haul cover soil | NOBS | MTI Outslope | 777F | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Haul cover soil | Reclaim Pond Outlet Channel | MTI Top | 777F | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Haul cover soil | NOBS | Tailing Pipeline Corridor | 777F | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
Haul cover soil | NOBS | Grape Gulch Pond #3 | 777F | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Haul cover soil | NOBS | Magnetite Seepage Pond | 777F | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 1 | 777F | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 2 | 777F | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Haul cover soil | OB Stockpile 1 through 3, Topsoil Stockpile, South OB Stockpile | SWRF Dam 3 | 777F | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Haul cover soil | OB-4 Stockpile | North Tailings Decant Pond | 777F | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Haul cover soil | OB-4 Stockpile | East WRF Containment | 777F | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Haul cover soil | NOBS | Blackman's Seep (Pond #2) | 777F | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3
Haul cover soil | OB-4 Stockpile | Decant Pond #4 | 777F | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Haul cover soil | NOBS | Upper Creek Containment Pond 1 | 777F | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3

## Earthwork.xls
Cobre
Stockpile Worksheet #4a
Earthwork Quantity Worksheet |  |  |  | 2014-12-05
SLOPE MODIFICATION
Dozer
Description | Location 1 | Location 2 | Push | Volume
|  |  | (feet) | (CY)
Regrade Top | SWRDF | - | 540 | 666680
Regrade Top | MTI | - | 200 | 50794.5
Regrade Outslope | MTI Reclaim Pond | - | 200 | 67765
Regrade Outslope | MTI | - | 250 | 170294
Reclaim Pond Outlet Channel | MTI Top | - | - | 62226