## Basis
NMCC-FIN-FA-007 — Progressive Financial Assurance Liability Model, Rev E (SRCE September 2026 r0 phased to the MORP mine plan; 25 Oct 2026)
This workbook builds the progressive financial assurance schedule from the September 2026 SRCE (r0) and the MORP mine plan. Each SRCE account is tied to a physical driver from MORP Tables 3 and 4 so that liability grows only as the corresponding disturbance is created. Yellow cells are inputs (SRCE directs, MORP quantities, credit weights). Green cells are calculated. Orange cells are totals. Everything is in 2026 dollars; each three-year review re-prices to then-current dollars. Tranche 1 uses the NMED-approved Existing Conditions Closure Plan amount ($5,728,244). From Tranche 2 onward the model uses the full September 2026 SRCE.
SRCE r0 account (2026 Financial Assurance Calculation, Table 1 / Acct Codes sheet) | Direct ($) | Liability driver (this model) | SRCE composition (FA Schedule sheet)
Waste rock — existing stockpiles (EWRSP-1, -2A, -2B, -3, -4) | 2933506 | In place at issuance (100%) | EWRSP regrade/cover/reveg $1,764,511; EWRSP channels $956,787; EWRSP-2A relocation $59,724; EWRSP setback/armor $120,058; yards $32,426
Waste rock — new stockpiles WRSP-1, -2, -3 | 9136213 | Cumulative waste tons placed ÷ 44,682,000 st (MORP Table 3) | WRSP regrade/cover/reveg $3,653,352; WRSP channels $4,302,307; ACB and slope armor $1,176,789; yards $3,765
Waste rock account — site disturbance (growth-media stockpiles, land bridges, pit-perimeter disturbance) | 429101 | Construction: 60% 2028, 100% 2029 (MORP Table 4 Years 1–2) | GM-01/02/03 footprints $279,757; land bridges $15,825; pit perimeter disturbance $113,897; channels $5,733; other $13,889
Tailings storage facility (DSTSF) | 15468903 | Cumulative DSTSF stage footprint constructed ÷ 487 ac (MORP Table 4 CST Phases 1–5) | Stack regrade/cover/reveg $8,884,531; stormwater channels and dissipaters $5,528,634; ACB, slope armor, liner demolition, channel prep $1,053,228; yards $2,510
Open pit (perimeter channel, ACB, pit-area reclamation, fence, signs) | 5589661 | Cumulative pit disturbance ÷ 165 ac (MORP Table 4 Years 2, 3, 5, 6) | ACB $4,094,005; pit areas reclaimed $795,993; perimeter channel PC-1 $581,820; fence and replacements $100,200; HC-5 $15,361; signs $2,282
Pit rapid fill (pumping, 3 years) | 1493148 | Attaches as the pit advances below the water table: 0% 2030, 25% 2031, 50% 2032, 75% 2033, 100% 2034 (planning assumption — PE to confirm from the pit schedule) | Rapid fill Yr 1–3 $1,297,038; well-field pumping $196,110
Buildings, foundations, tanks, process equipment demolition, mill decontamination | 3958805 | Fixed at mechanical completion: 50% 2028, 100% 2029 | Buildings and foundations $3,103,538; tank and equipment demolition $547,758; mill decon $172,799; property fence $134,710
Roads | 87348 | Construction: 60% 2028, 100% 2029 | Road reclamation $71,050; regrading $16,298
Impoundments (SW-A/B/C, DSTSF seepage pond, PC-04) | 753013 | Construction: 60% 2028 (TSF pond, SW-A), 100% 2029 (SW-B, SW-C) | Ponds $614,381; PC-04 $138,632
Yards and plant-area disturbance | 1336490 | Construction: 70% 2028, 100% 2029 | Plant disturbance $318,202; plant channels $566,402; pullback and land-bridge excavations $283,421; concentrator area $100,247; conveyor trench backfill $65,002; liner ditches $3,216
Monitoring well closure and repair (55 wells) | 328489 | Existing network at issuance 80%; 100% 2029 (new wells) | Well abandonment $297,289; repairs $31,200
Waste disposal (solid, hazardous, used oils and fluids) | 116259 | 100% 2029 (first operations) | Oils and fluids $106,352; lab and solid waste $9,906
Miscellaneous linear facilities (tailings conveyor, pipelines, on-site powerline) | 1940723 | Construction: 40% 2028, 100% 2029 | Conveyor $1,625,000; pipelines $237,160; powerline $78,563
Monitoring (100-year water-quality; 12-year reclamation performance) | 3865851 | 100% from construction start (DP-1840 post-closure obligation attaches with the facilities) | Well monitoring $3,056,762; surface water $601,499; field work, reporting, DST and wildlife monitoring $180,990; pump $26,600
Reclamation maintenance (cover repair 5%, reseeding 10%) | 866143 | Proportional to waste rock + DSTSF liability in place | Growth media $601,935; revegetation $224,968; ditch maintenance $39,240
Mobilization / demobilization | 644762 | 100% from construction start (any reclamation contract mobilizes) | Fleet per Exhibit 1
Construction management (active reclamation) | 2331441 | 4.72% of all other direct liability in place (SRCE ratio) | $721,358 + $1,610,083
Riprap supply | 427329 | Proportional to waste rock + DSTSF + pit liability in place | Supply $283,782; haul from pit $143,547
Subtotal direct cost (SRCE r0: $51,707,185) | 51707185
Check against SRCE r0 subtotal | 0
Indirect rates (SRCE r0)
Engineering, design and construction plan | 4%
Contingency | 6%
Contractor overhead and profit | 10%
Contract administration and procurement | 11.93%
Total indirect loading on direct | 31.93%
Indirect cost at full build-out (SRCE r0: $16,511,662) | 16511661.6617
Total reclamation cost, 2026 dollars (SRCE r0: $68,218,847) | 68218846.6617
Financial assurance parameters
Contingency on net liability (NMCC margin above the SRCE) | 15%
Minimum contingency margin ($) | 5000000
Credit weight — Tier 1 and Tier 2 (earthwork and cover verified; seeded) | 30%
Credit weight — Tier 3 and Tier 4 (vegetation success verified; partial release) | 100%
Disturbed (bond) area (ac) — MORP Table 2 | 1191
Pit lake, not reclaimed (ac) — MORP Table 5 | 74
Reclaimable area (ac) — credit denominator = disturbed area less pit lake | 1117
Years from Tier 1 to Tier 3 verification (growing seasons) | 3
Construction management ratio to other directs (SRCE r0) | 4.722%
Tranche 1 (permit issuance) — Existing Conditions Closure Plan SRCE, NMED-approved
ECCP direct (Addendum rA, 18 Jun 2025, Table 1) | 4582595
ECCP indirect (3/5/7/10%) | 1145649
ECCP total — approved amount and letter-of-credit basis | 5728244
Letter of credit (DP-1840 C115.L) | 5700000
Calendar (MPR Rev 14 / MORP Table 4): MORP Year n = 2027 + n; production Year p = 2029 + p. Permit issuance Q4 2026; NTP 31 Dec 2027 (Year 1 = 2028); first ore 28 Feb 2030 (Year 3); end of mining Year 14 = 2041; post-operation reclamation Years 14–18 (2041–2045); post-closure monitoring from Year 19 (2046) for 100 years.

## Notes
How the model is built, and the assumptions behind it
The main drivers
• | Waste rock liability grows with cumulative tons placed.
• | DSTSF liability grows with stage footprint constructed (not with tons of tailings).
• | Pit liability grows with cumulative pit disturbance.
• | Buildings and plant demolition liability is fixed at mechanical completion.
• | Pit rapid-fill liability attaches as the pit advances below the water table (planning assumption — PE to confirm).
• | Monitoring, mobilization, and the long-term accounts attach when construction starts.
Key assumptions
• | DSTSF liability is driven by stage footprint constructed, not by tons of tailings placed. Using tons would lower the early postings; we kept the footprint basis because the liner and channels are the bulk of the cost and are built with the stage.
• | Pit rapid-fill liability is phased in as a planning assumption (0% in 2030, rising to 100% in 2034). The PE will confirm the timing against the actual pit schedule.
• | The 30% weight on Tier 1/2 and the three-year lag to Tier 3 are judgments. They can be changed in the yellow input cells on the Basis sheet if the agencies prefer different weights or a different verification period.
• | The model does not credit reclamation beyond the permitted Table 4 sequence. Faster concurrent reclamation improves the credit only after NMMMD verifies it.

## Drivers
Physical drivers by calendar year — MORP Rev 2 Table 3 (production schedule) and Table 4 (build-out and reclamation sequence)
The driver sheet pulls quantities straight from MORP Tables 3 and 4. Waste rock and ore are annual production. DSTSF stage footprints, pit disturbance, and waste-rock footprints are the build-out sequence. Reclaimed acres follow the Table 4 reclamation sequence as permitted. We did not credit our accelerated reclamation target (240–280 acres by year 12) in the base case; the credit shown is only what the permitted sequence produces. If we reclaim faster and NMMMD verifies it, the credit will be higher at the reviews; the model does not assume that.
Driver | Total / unit | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
MORP year |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
Waste rock mined (st) — Table 3 | 44682000 |  |  |  | 110000 | 8560000 | 6700000 | 6700000 | 6700000 | 6700000 | 5924000 | 2491000 | 718000 | 71000 | 3000 | 1000 | 4000
Ore processed / tailings produced (st) — Table 3 | 113084000 |  |  |  |  | 9300000 | 10800000 | 10800000 | 10800000 | 10800000 | 10025000 | 9900000 | 9900000 | 9900000 | 9900000 | 9900000 | 1059000
DSTSF stage footprint constructed (ac) — Table 4 CST Phases 1–5 | 487 |  |  | 2028 1: 161; 2031 4: 101; 2033 6: 106; 2035 8: 52; 2037 10: 67
Open pit disturbance (ac) — Table 4 | 165 |  |  | 2029 2: 83; 2030 3: 66; 2032 5: 8; 2033 6: 8
WRSP-1/2/3 footprint disturbed (ac) — Table 4 | 236 |  |  | 2029 2: 12; 2030 3: 51; 2031 4: 46; 2032 5: 33; 2033 6: 23; 2034 7: 20; 2035 8: 18; 2036 9: 6
Plant, ancillary, roads, impoundments, stockpiles disturbed (ac) — Table 4 |  |  |  | 2028 1: 325; 2029 2: 170
Acres reclaimed to Tier 1 (graded, covered, seeded) — Table 4 reclamation sequence | 1117 |  |  |  | 36 |  |  | 20 |  | 20 |  | 30 | 10 | 30 | 30 | 10 | 96 | 221 | 249 | 226 | 142
of which concurrent (during construction and operations, 2029–2040) | 186
of which post-operation (2041–2045) | 934
Cumulative waste placed (fraction of LOM) → WRSP liability |  | 0% | 0% | 0% | 0.2462% | 19.4% | 34.4% | 49.39% | 64.39% | 79.38% | 92.64% | 98.22% | 99.82% | 99.98% | 99.99% | 99.99% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Cumulative tailings produced (fraction of LOM) — comparison basis for the DSTSF |  | 0% | 0% | 0% | 0% | 8.224% | 17.77% | 27.32% | 36.88% | 46.43% | 55.29% | 64.05% | 72.8% | 81.55% | 90.31% | 99.06% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Cumulative DSTSF footprint constructed (fraction) → DSTSF liability |  | 0% | 0% | 33.06% | 33.06% | 33.06% | 53.8% | 53.8% | 75.56% | 75.56% | 86.24% | 86.24% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Cumulative pit disturbance (fraction) → pit liability |  | 0% | 0% | 0% | 50.3% | 90.3% | 90.3% | 95.15% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Construction accrual — buildings (mechanical completion Oct 2029) |  | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Construction accrual — yards |  | 0% | 0% | 70% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Construction accrual — roads, impoundments, site disturbance |  | 0% | 0% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Construction accrual — linear facilities (conveyor, pipelines, powerline) |  | 0% | 0% | 40% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Wells — existing network at issuance, new wells by first ore |  | 80% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Waste disposal — from first operations |  | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Mobilization and monitoring — from construction start |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Pit rapid fill — pit below water table (planning assumption) |  | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Existing stockpiles — in place at issuance |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Sources: MORP Update 2025 Rev 2 (22 Jun 2026) Tables 2, 3 and 4; MPR Rev 14 schedule (NTP 31 Dec 2027; first ore 28 Feb 2030). Reclaimed acres are the Table 4 sequence as permitted (36 ac existing stockpiles in Year 2; 20 ac DSTSF concurrent cover in Years 5, 7, 9, 11, 12; 10 ac/yr WRSP concurrent grading Years 9–13; post-operation Years 14–18). NMCC's accelerated target of 240–280 ac by operations Year 12 is not credited in the base case.

## Liability
In-place reclamation liability by calendar year — SRCE r0 directs × driver fraction (2026 dollars)
Each cell = Basis!direct × Drivers!fraction at year end. Liability accrues when ground is disturbed or a facility is built, not when reclamation is scheduled.
Account | Direct ($) | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
Waste rock — existing stockpiles (EWRSP-1, -2A, -2B, -3, -4) | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506 | 2933506
Waste rock — new stockpiles WRSP-1, -2, -3 | 9136213 | 0 | 0 | 0 | 22491.9079 | 1772771.2884 | 3142732.9531 | 4512694.6177 | 5882656.2824 | 7252617.947 | 8463909.4249 | 8973248.9035 | 9120059.7207 | 9134577.2249 | 9135190.6405 | 9135395.1124 | 9136213 | 9136213 | 9136213 | 9136213 | 9136213 | 9136213 | 9136213
Waste rock account — site disturbance (growth-media stockpiles, land bridges, pit-perimeter disturbance) | 429101 | 0 | 0 | 257460.6 | 429101 | 429101 | 429101 | 429101 | 429101 | 429101 | 429101 | 429101 | 429101 | 429101 | 429101 | 429101 | 429101 | 429101 | 429101 | 429101 | 429101 | 429101 | 429101
Tailings storage facility (DSTSF) | 15468903 | 0 | 0 | 5113949.4517 | 5113949.4517 | 5113949.4517 | 8322079.232 | 8322079.232 | 11689027.3183 | 11689027.3183 | 13340737.7002 | 13340737.7002 | 15468903 | 15468903 | 15468903 | 15468903 | 15468903 | 15468903 | 15468903 | 15468903 | 15468903 | 15468903 | 15468903
Open pit (perimeter channel, ACB, pit-area reclamation, fence, signs) | 5589661 | 0 | 0 | 0 | 2811768.8667 | 5047633.2667 | 5047633.2667 | 5318647.1333 | 5589661 | 5589661 | 5589661 | 5589661 | 5589661 | 5589661 | 5589661 | 5589661 | 5589661 | 5589661 | 5589661 | 5589661 | 5589661 | 5589661 | 5589661
Pit rapid fill (pumping, 3 years) | 1493148 | 0 | 0 | 0 | 0 | 0 | 373287 | 746574 | 1119861 | 1493148 | 1493148 | 1493148 | 1493148 | 1493148 | 1493148 | 1493148 | 1493148 | 1493148 | 1493148 | 1493148 | 1493148 | 1493148 | 1493148
Buildings, foundations, tanks, process equipment demolition, mill decontamination | 3958805 | 0 | 0 | 1979402.5 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805 | 3958805
Roads | 87348 | 0 | 0 | 52408.8 | 87348 | 87348 | 87348 | 87348 | 87348 | 87348 | 87348 | 87348 | 87348 | 87348 | 87348 | 87348 | 87348 | 87348 | 87348 | 87348 | 87348 | 87348 | 87348
Impoundments (SW-A/B/C, DSTSF seepage pond, PC-04) | 753013 | 0 | 0 | 451807.8 | 753013 | 753013 | 753013 | 753013 | 753013 | 753013 | 753013 | 753013 | 753013 | 753013 | 753013 | 753013 | 753013 | 753013 | 753013 | 753013 | 753013 | 753013 | 753013
Yards and plant-area disturbance | 1336490 | 0 | 0 | 935543 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490 | 1336490
Monitoring well closure and repair (55 wells) | 328489 | 262791.2 | 262791.2 | 262791.2 | 328489 | 328489 | 328489 | 328489 | 328489 | 328489 | 328489 | 328489 | 328489 | 328489 | 328489 | 328489 | 328489 | 328489 | 328489 | 328489 | 328489 | 328489 | 328489
Waste disposal (solid, hazardous, used oils and fluids) | 116259 | 0 | 0 | 0 | 116259 | 116259 | 116259 | 116259 | 116259 | 116259 | 116259 | 116259 | 116259 | 116259 | 116259 | 116259 | 116259 | 116259 | 116259 | 116259 | 116259 | 116259 | 116259
Miscellaneous linear facilities (tailings conveyor, pipelines, on-site powerline) | 1940723 | 0 | 0 | 776289.2 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723 | 1940723
Monitoring (100-year water-quality; 12-year reclamation performance) | 3865851 | 0 | 0 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851 | 3865851
Reclamation maintenance (cover repair 5%, reseeding 10%) | 866143 | 90848.8577 | 90848.8577 | 257198.0888 | 263210.2457 | 317415.3104 | 459195.9573 | 501622.8186 | 648321.9697 | 690748.8311 | 779414.2194 | 795188.1465 | 865642.743 | 866092.3411 | 866111.3382 | 866117.6705 | 866143 | 866143 | 866143 | 866143 | 866143 | 866143 | 866143
Mobilization / demobilization | 644762 | 0 | 0 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762 | 644762
Construction management (active reclamation) | 2331441 | 156977.4944 | 156977.4944 | 832777.0781 | 1168644.7579 | 1361820.1848 | 1605063.5041 | 1703163.6815 | 1967193.6634 | 2052334.0558 | 2193428.402 | 2218529.6503 | 2330644.9347 | 2331360.3858 | 2331390.6161 | 2331400.6929 | 2331441 | 2331441 | 2331441 | 2331441 | 2331441 | 2331441 | 2331441
Riprap supply | 427329 | 37356.076 | 37356.076 | 105757.0957 | 144035.0718 | 194795.7281 | 253094.4095 | 273991.0454 | 337763.3284 | 355208.7988 | 391667.0556 | 398153.1252 | 427123.2997 | 427308.1696 | 427315.981 | 427318.5848 | 427329 | 427329 | 427329 | 427329 | 427329 | 427329 | 427329
Direct liability in place | 51707185 | 3481479.6281 | 3481479.6281 | 18469503.8144 | 25918447.3018 | 30202732.2302 | 35597433.3227 | 37773119.5286 | 43628831.5623 | 45517092.951 | 48646312.802 | 49203013.5257 | 51689529.698 | 51705397.1213 | 51706067.5758 | 51706291.0607 | 51707185 | 51707185 | 51707185 | 51707185 | 51707185 | 51707185 | 51707185
Indirects (SRCE r0 loading) | 16511661.6617 | 1111741.3122 | 1111741.3122 | 5897868.8947 | 8276540.9226 | 9644642.1487 | 11367332.7033 | 12062094.8435 | 13932000.0779 | 14534978.8164 | 15534232.9712 | 15712004.2808 | 16506023.7919 | 16511090.7381 | 16511304.8345 | 16511376.1999 | 16511661.6617 | 16511661.6617 | 16511661.6617 | 16511661.6617 | 16511661.6617 | 16511661.6617 | 16511661.6617
GROSS IN-PLACE LIABILITY (third-party, 2026 $) | 68218846.6617 | 4593220.9403 | 4593220.9403 | 24367372.709 | 34194988.2243 | 39847374.3789 | 46964766.026 | 49835214.3722 | 57560831.6402 | 60052071.7674 | 64180545.7732 | 64915017.8065 | 68195553.49 | 68216487.8595 | 68217372.4103 | 68217667.2606 | 68218846.6617 | 68218846.6617 | 68218846.6617 | 68218846.6617 | 68218846.6617 | 68218846.6617 | 68218846.6617
Gross as fraction of full life-of-mine calculation |  | 6.733% | 6.733% | 35.72% | 50.13% | 58.41% | 68.84% | 73.05% | 84.38% | 88.03% | 94.08% | 95.16% | 99.97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Long-term accounts held in full — monitoring, reclamation maintenance, wells — with indirects (not reduced by acreage credit) | 6676447.6506 | 466567.9803 | 466567.9803 | 5786371.2005 | 5880980.3067 | 5952494.6812 | 6139550.1593 | 6195525.1954 | 6389069.8042 | 6445044.8404 | 6562023.7579 | 6582834.7751 | 6675787.6464 | 6676380.8147 | 6676405.8782 | 6676414.2326 | 6676447.6506 | 6676447.6506 | 6676447.6506 | 6676447.6506 | 6676447.6506 | 6676447.6506 | 6676447.6506
Credit base — gross in-place liability less the long-term accounts (the part acreage credit applies to) | 61542399.0111 | 4126652.96 | 4126652.96 | 18581001.5085 | 28314007.9176 | 33894879.6977 | 40825215.8667 | 43639689.1767 | 51171761.8359 | 53607026.927 | 57618522.0153 | 58332183.0315 | 61519765.8436 | 61540107.0448 | 61540966.5321 | 61541253.0279 | 61542399.0111 | 61542399.0111 | 61542399.0111 | 61542399.0111 | 61542399.0111 | 61542399.0111 | 61542399.0111

## Credit
Tier-weighted verified reclamation credit by year end — MORP Table 4 reclamation sequence as the base case
Credit is calculated only on NMMMD-verified acres and is applied only to the reclaimable portion of the liability (gross in-place less the long-term accounts). The long-term accounts stay in full until release. Acres that have reached Tier 1 or 2 in the last three years count at 30%. Acres whose Tier 1 date is at least three years earlier and that have met vegetation success count at 100%. Weighted acres are divided by the 1,117 reclaimable acres. The three-year lag from Tier 1 to Tier 3 is a planning assumption; actual credit at each review will be whatever NMMMD has verified by that date.
Item | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
Acres reaching Tier 1 in year (Drivers row 14) | 0 | 0 | 0 | 36 | 0 | 0 | 20 | 0 | 20 | 0 | 30 | 10 | 30 | 30 | 10 | 96 | 221 | 249 | 226 | 142 | 0 | 0
Cumulative acres at Tier 1 or better | 0 | 0 | 0 | 36 | 36 | 36 | 56 | 56 | 76 | 76 | 106 | 116 | 146 | 176 | 186 | 282 | 503 | 752 | 978 | 1120 | 1120 | 1120
Acres at Tier 3/4 (Tier 1 year ≤ year − LAG) | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 36 | 56 | 56 | 76 | 76 | 106 | 116 | 146 | 176 | 186 | 282 | 503 | 752 | 978
Acres at Tier 1/2 (not yet Tier 3) | 0 | 0 | 0 | 36 | 36 | 36 | 20 | 20 | 40 | 20 | 50 | 40 | 70 | 70 | 70 | 136 | 327 | 566 | 696 | 617 | 368 | 142
Weighted credit acres | 0 | 0 | 0 | 10.8 | 10.8 | 10.8 | 42 | 42 | 48 | 62 | 71 | 88 | 97 | 127 | 137 | 186.8 | 274.1 | 355.8 | 490.8 | 688.1 | 862.4 | 1020.6
Credit fraction of reclaimable area | 0% | 0% | 0% | 0.9669% | 0.9669% | 0.9669% | 3.76% | 3.76% | 4.297% | 5.551% | 6.356% | 7.878% | 8.684% | 11.37% | 12.26% | 16.72% | 24.54% | 31.85% | 43.94% | 61.6% | 77.21% | 91.37%
Credit fraction — no verified reclamation (sensitivity) | bar: 2026 to 2047

## Reviews
Posting and three-year review schedule — reviews every three years from permit issuance (Q4 2026)
Required amount at any date = (gross in-place liability − long-term accounts) × (1 − verified credit) + long-term accounts + contingency. Contingency is the greater of 15% of the net or $5 million. During construction we post the increment before each construction year. From first ore onward each posting covers the greater of the amount required at that review and the amount projected for the next review, so the State is not holding less than the in-place liability between reviews. Reductions occur only at a review and only on verified reclamation. The sensitivity cases (no credit, and DSTSF accrued by tons instead of footprint) are shown so the effect of those assumptions can be seen directly.
Milestone | Date | Liability year-end used | Direct in place ($) | Gross in-place liability ($) | Long-term accounts held in full ($) | Verified credit (%) | Net liability ($) | Contingency ($) | Required FA at this date ($) | Posted — covers through next review ($) | Posted ($M) | Basis / note
Tranche 1 — permit issuance | Q4 2026 | ECCP | 4582595 | 5728244 | 0 | 0% | 5728244 | 0 | 5700000 | 5700000 | 5.7 | ECCP SRCE $5,728,244 approved by NMED; $5.7M letter of credit (DP-1840 C115.L). Whole in-place liability at issuance is the existing-conditions site.
Tranche 2 — before Notice to Proceed | Dec 2027 | 2028 | 18469503.8144 | 24367372.709 | 5786371.2005 | 0% | 24367372.709 | 5000000 | 29367372.709 | 29367372.709 | 29 | Covers liability created in construction year 1 (plant site and buildings, DSTSF Stage 1 liner, linear facilities, monitoring and mobilization obligations)
Tranche 3 — before construction year 2 | Dec 2028 | 2029 | 25918447.3018 | 34194988.2243 | 5880980.3067 | 0.9669% | 33921227.0019 | 5088184.0503 | 39009411.0521 | 39009411.0521 | 39 | Covers end-of-construction position (pit pre-production, WRSP starts, remaining plant, SW-B/C); PE letter
Tranche 4 — first ore (Review 0) | Q1 2030 | 2029 | 25918447.3018 | 34194988.2243 | 5880980.3067 | 0.9669% | 33921227.0019 | 5088184.0503 | 39009411.0521 | 55423480.4248 | 55 | First PE-certified recalculation on the as-built site; posting carried to the Review 1 projection; EWRSP-1/-2A/-2B at Tier 1
Review 1 — operations year 3 | Q4 2032 | 2032 | 37773119.5286 | 49835214.3722 | 6195525.1954 | 3.76% | 48194330.8042 | 7229149.6206 | 55423480.4248 | 70129739.8865 | 70 | DSTSF Stage 2 built; waste placement 49% of LOM; EWRSP credit at Tier 3
Review 2 — operations year 6 | Q4 2035 | 2035 | 48646312.802 | 64180545.7732 | 6562023.7579 | 5.551% | 60982382.51 | 9147357.3765 | 70129739.8865 | 72303214.4485 | 72 | Stage 4 built; waste placement 91%; pit rapid-fill obligation in full
Review 3 — operations year 9 | Q4 2038 | 2038 | 51705397.1213 | 68216487.8595 | 6676380.8147 | 8.684% | 62872360.39 | 9430854.0585 | 72303214.4485 | 72303214.4485 | 72 | Full build-out — peak liability; concurrent DSTSF and WRSP-3 credits
Review 4 — end of operations | Q4 2041 | 2041 | 51707185 | 68218846.6617 | 6676447.6506 | 16.72% | 57926885.9318 | 8689032.8898 | 66615918.8215 | 66615918.8215 | 67 | Mining and processing ended Year 14; post-operation reclamation begins
Review 5 — closure execution | Q4 2044 | 2044 | 51707185 | 68218846.6617 | 6676447.6506 | 43.94% | 41177656.4784 | 6176648.4718 | 47354304.9502 | 47354304.9502 | 47 | Post-operation reclamation largely at Tier 1/2; earlier work at Tier 3
Review 6 — post-closure transition | Q4 2047 | 2047 | 51707185 | 68218846.6617 | 6676447.6506 | 91.37% | 11987716.4641 | 5000000 | 16987716.4641 | 16987716.4641 | 17 | Reclamation complete Year 18 (2045); remaining liability = monitoring, maintenance, well closure (post-closure instrument)
Post-closure instrument (put in place at Review 6, 2047; monitoring period from 2046): monitoring, reclamation maintenance, well closure and repair, with indirects and contingency |  |  |  | 6676447.6506 |  |  |  |  | 7677914.7982 | 7677914.7982 | 7.7 | 100-year water-quality monitoring (DP-1840 C115.K.1), 12-year reclamation performance monitoring, cover and revegetation maintenance; held until NMMMD and NMED release
Sensitivity — required FA with NO verified reclamation credit ($M)
Tranche 2 — before Notice to Proceed |  | 2028 |  | 24367372.709 |  |  |  |  | 29367372.709 |  | 29
Tranche 3 — before construction year 2 |  | 2029 |  | 34194988.2243 |  |  |  |  | 39324236.458 |  | 39
Tranche 4 — first ore (Review 0) |  | 2029 |  | 34194988.2243 |  |  |  |  | 39324236.458 |  | 39
Review 1 — operations year 3 |  | 2032 |  | 49835214.3722 |  |  |  |  | 57310496.528 |  | 57
Review 2 — operations year 6 |  | 2035 |  | 64180545.7732 |  |  |  |  | 73807627.6391 |  | 74
Review 3 — operations year 9 |  | 2038 |  | 68216487.8595 |  |  |  |  | 78448961.0384 |  | 78
Review 4 — end of operations |  | 2041 |  | 68218846.6617 |  |  |  |  | 78451673.6609 |  | 78
Review 5 — closure execution |  | 2044 |  | 68218846.6617 |  |  |  |  | 78451673.6609 |  | 78
Review 6 — post-closure transition |  | 2047 |  | 68218846.6617 |  |  |  |  | 78451673.6609 |  | 78
Sensitivity — required FA with the DSTSF accrued by tailings tonnage instead of stage footprint ($M, same credits)
Tranche 2 — before Notice to Proceed |  | 2028 |  | 17620385.1582 | 5786371.2005 | 0% | 17620385.1582 |  | 22620385.1582 |  | 23
Tranche 3 — before construction year 2 |  | 2029 |  | 27448000.6735 | 5880980.3067 | 0.9669% | 27239474.4246 |  | 32239474.4246 |  | 32
Tranche 4 — first ore (Review 0) |  | 2029 |  | 27448000.6735 | 5880980.3067 | 0.9669% | 27239474.4246 |  | 32239474.4246 |  | 32
Review 1 — operations year 3 |  | 2032 |  | 44432255.0609 | 6195525.1954 | 3.76% | 42994526.6327 |  | 49443705.6276 |  | 49
Review 2 — operations year 6 |  | 2035 |  | 57863772.4708 | 6562023.7579 | 5.551% | 55016226.8842 |  | 63268660.9169 |  | 63
Review 3 — operations year 9 |  | 2038 |  | 64452005.0681 | 6676380.8147 | 8.684% | 59434784.3406 |  | 68350001.9917 |  | 68
Review 4 — end of operations |  | 2041 |  | 68218846.6617 | 6676447.6506 | 16.72% | 57926885.9318 |  | 66615918.8215 |  | 67
Review 5 — closure execution |  | 2044 |  | 68218846.6617 | 6676447.6506 | 43.94% | 41177656.4784 |  | 47354304.9502 |  | 47
Review 6 — post-closure transition |  | 2047 |  | 68218846.6617 | 6676447.6506 | 91.37% | 11987716.4641 |  | 16987716.4641 |  | 17

## Glossary
Glossary
SRCE | Standardized Reclamation Cost Estimator (BLM / Nevada / SRK), version 2.0; file 2026 CF SRCE r0.xlsm, September 2026
r0 | Revision 0 of the September 2026 SRCE calculation provided to NMMMD (total $68,218,847)
Direct cost | Labor, equipment and materials for each SRCE account, third-party contractor basis, 2026 dollars
Indirects | Engineering 4%, contingency 6%, contractor OH&P 10%, contract administration and procurement 11.93% (SRCE r0 rates)
In-place liability | Third-party cost to reclaim the disturbance that exists at a date, on the SRCE basis
Tier 1–4 | NMCC verification tiers: 1 graded and covered (field-verified); 2 seeded, first season; 3 vegetation success verified (19.10.6.603.G); 4 partial release
Credit | Tier-weighted verified reclaimed acres ÷ reclaimable area (1,117 ac), applied to the gross liability less the long-term accounts (monitoring, reclamation maintenance, wells), which are held in full until release
Contingency | NMCC margin on net liability (15%, minimum $5M), in addition to the SRCE 6% contingency
MORP | Mine Operation and Reclamation Plan, Permit SI027RN; Update 2025 Rev 2 (22 Jun 2026)
DSTSF | Dry stack tailings storage facility (486–487 ac; five stages)
WRSP / EWRSP | Waste rock stockpile (new) / existing waste rock stockpile
ECCP | Existing Conditions Closure Plan (NMED-approved, DP-1840 Amendment 18-01)
NTP | Notice to Proceed with construction (31 Dec 2027)
PE | New Mexico-licensed professional engineer