## Slide 1
Carlsbad Brine Well Authority Meeting
June 02, 2022

## Slide 2
Jim Griswold - OCD
Dan Kwiecinski – Wood Project Manager
Peter Guerra – Wood Deputy PM
Introductions

## Slide 3
Project Background
Work Completed
  Remediation Design
  Filling the Cavity
Work Remaining
  Cavity Depressurization
  Site Surface Restoration Activities
  Post-remediation Monitoring
  Project Closeout
Meeting the Project Objectives
Discussion
Agenda

## Slide 4
Remediation Implementation Work Completed
2018-2019 – Remediation Plan Design
Sep 2019 - Mobilization
  Grouting Campaign
    Stabilize Southern Cavity
    Injected 5,600 CY of Grout
  Discovered Northern Void
    December 2019 Encountered During Drilling
    February 2020 Sonar Survey
  Required adjustment to remediation approach
  Sand Slurry Campaign
    Stabilize Northern Void
    Injected 170,000 CY of Sand
    Completed Feb 2022
  Brine removed and disposed of from cavity equal to the volume of solids added.
Apr 2022 - Demobilization
SAND STABILIZED
NORTHERN VOID
ORIGINAL
BOUNDARY
GROUT STABILIZED
SOUTHERN VOID

## Slide 5
Filling the Northern Void Work Completed
FEBRUARY 2020
MAY 2020
SEPTEMBER 2021
JANUARY 2022
SAND FILLED CAVITY
SAND FILLED RUBBLE
(CONCEPTUAL)
500’
400’
300’
0’
100’
100’
GW3
GW5

## Slide 6
Cavity Depressurization Work Remaining
Objectives
  Decrease pressure of brine in cavity
  Protect freshwater aquifer
Stepwise Depressurization
  Decrease cavity pressure incrementally
  Monitor performance with existing instrumentation
  Ease off pressure to preserve integrity of aquitard (barrier between cavity and freshwater aquifer)
AQUITARD
FRESH
GROUND
WATER
GROUT/SAND
AND BRINE
FILLED CAVITY
CURRENT BRINE LEVEL
(~60-ft or 32 psi above ground)
TARGET BRINE LEVEL
(~60-ft or 32 psi below ground)

## Slide 7
Site Surface Restoration Work Remaining
Demobilize equipment and unused materials
Restore / Replace
  Grades and pavements
  Fencing and gates
  Septic System
Remove Project Infrastructure
  Site Office
  Storage buildings
  Surface water control features
  Brine storage

## Slide 8
Post-remediation Monitoring Work Remaining
Two years of monitoring following depressurization
What will be monitored?
  Existing monitoring system to measure changes subsurface
  Brine and sand level in cavity
  (gauging using water-level sounder)
  Fresh groundwater quality
  Ground surface movement (InSAR)
Why is it smart to monitor?
  Adjust level of brine if rising
  Assess condition of cavity before plugging wells
  Assure freshwater quality is maintained
Quarterly reporting

## Slide 9
Meeting the Project Objectives
Mitigate the risk of a sinkhole forming at the project site and surrounding area.
  With the completion of sand deployment at the northern void the risk of a sinkhole forming at the surface has been mitigated to the extent possible.
Protect the freshwater aquifer above the cavity from brine impacts.
  A significant portion of the risk of brine and freshwater mixing due to a cavity roof collapse was abated by filling the cavity with grout and sand.
  Carefully lowering the brine level (stepwise depressurization) will further reduce the risk of brine from the cavity impacting the freshwater above.

## Slide 10
Discussion
Source: https://www.travellens.co/best-things-to-do-in-carlsbad-nm/

## Slide 11
Appendix

## Slide 12
Project Background
1978
2008
2010
2012
2014
2016
2018
ACTIVE SOLUTION MINING
PRELIMINARY
INVESTIGATIONS
SITE CHARACTERIZATION
& FEASIBILTY STUDY
Operated from 1978 until July of 2008.
Dissolving and extracting the subsurface salt deposit in the form of brine (salt-laden water).
Two wells named Eugenie #1 and Eugenie #2 used in brine production.
A fracking procedure at Eugenie #2 was conducted in late 1979 to increase brine production.
Eugenie #1
Eugenie #2
2005

## Slide 13
1978
2008
2010
2012
2014
2016
2018
ACTIVE SOLUTION MINING
PRELIMINARY
INVESTIGATIONS
SITE CHARACTERIZATION
& FEASIBILTY STUDY
7/16/2008: Brine well southeast of Artesia catastrophically collapsed forming a 100-ft deep sinkhole.
7/22/2008: Brine production at the site was terminated at OCD’s direction.
11/3/2008: Second brine well collapse occurred north of Loco Hills, NM.
Project Background

## Slide 14
1978
2008
2010
2012
2014
2016
2018
ACTIVE SOLUTION MINING
PRELIMINARY
INVESTIGATIONS
SITE CHARACTERIZATION
& FEASIBILTY STUDY
Geophysical surveys were performed from 2009 to 2012 to provide an initial understanding of the cavity.
Geophysical methods include:
  Seismic reflection and refraction,
  Reflection microtremor (ReMi),
  High-resolution magnetotelluric (MT) Z-Scan,
  Microgravity, and
  2-D electrical resistivity.
Project Background
Compilation of results from all the geophysical methods used to characterize the
cavity.

## Slide 15
1978
2008
2010
2012
2014
2016
2018
ACTIVE SOLUTION MINING
PRELIMINARY
INVESTIGATIONS
SITE CHARACTERIZATION
& FEASIBILTY STUDY
Coring and drilling campaigns
Cavity sonar surveys
Analysis and modeling of the cavity
InSAR to assess settlement / surface movement
Evaluate and select the remediation approach
Project Background

## Slide 16
Remediation Design (2018-19) Work Completed

## Slide 17
Continuous Monitoring
Remote Access and Online Reporting
Monitored 24/7 during Operations
MICROSEISMIC STATION
BOREHOLE TILT METER
Monitoring System Work Completed

## Slide 18
Monitoring System in Action Work Completed