## Sheet1
Summary of Changes made to FA spreadsheets after comments from MMD
Tailings Facility
Tab | Changes Made in November 2018
1e…Approach 2018-Update | Under Earthwork, explained scope change with Kiewits estimate. Tailing cover only performed with scrapers and graders.
1e…Approach 2018-Update | Added description of what is typically included in mobilization and demoblication costs (under Indirect Costs)
19..Inflation Rate | Updated source to All Urban All U.S. City for a 27-year average inflation rate of 2.36%
20..Discount Rate | Changed year 2017 Annual Index Rate from 4.21% to 3.54% (internet source had a typo that has since been fixed)
Tailings Facility
Tab | Changes Made in November 2018
General | Updated date and added note to date on General Tab "Updated includes comments from MMD/NMED April 2018"
1…Describe | Added note that Capulin is covered under the early design action FA and is excluded from this spreadsheet
1…Describe | Deleted Capulin
1…Describe | Added Pit Repository Pond to other list
1f…Approach 2018 | Added note that approach was conservative and is only an estimate until a more detailed design is approved
1f…Approach 2018 | Added description of what is typically included in mobilization and demoblication costs (under Indirect Costs)
1f…Approach 2018 | Added Capulin Borehole Re-Drill cost to list of O&M items
1f…Approach 2018 | Added Pit Repository Pond to other reclamation activities list
3…Material | Deleted Capulin items
4…Earthwrk | Deleted Capulin items
5…Dozer | Deleted Capulin items
6…Grading | Deleted Capulin items
8…Loader | Deleted Capulin items
9…Trucks | Deleted Capulin items
13…EarthSum | Deleted Capulin items
14…Reveg | Deleted Capulin items
14…Reveg | Added "Biosolid" to amendment description.
17…Other | Deleted Capulin items
17…Other | Added "Biosolid" to Amendment description.
17…Other | Added Pit Repository Pond Liner Cost. Cost Spreadout due to unknown project phasing.
18…O&M | Expanded on Other O&M Items descriptions.
18…O&M | Added pump replacement cost (based on actual install and estimated 20-year life)
21…Inflation Rate | Updated source to All Urban All U.S. City for a 27-year average inflation rate of 2.36%
22...Discount Rate | Changed year 2017 Annual Index Rate from 4.21% to 3.54% (internet source had a typo that has since been fixed)
20...NPV - CMI_2014 | Added two pump replacement occurences under other O&M in years 2035 and 2055 for Enhanced 005 Pump Station